Eastern Mediterranean University - Computer Engineering Department

Software Engineering Program

CMSE-201 Fundamentals of Software Engineering - Midterm Exam

Std Id____________________Std Name____________________________________

Instructor: Alexander G. Chefranov

Duration: 100 Minutes               				                      April 16, 2026, 8.30

--------------------------------------------------------------------------------------------------------------

Three A4 sheets of paper with your handwritings (not photocopies, printouts, etc.) may be used for your help. Calculators, telephones, other electronic devices are not allowed. Passing of any material (rubbers, pencils, etc.) is not allowed.

There are 5 questions (totally, 100 points), 5 pages

| Task | Q1 | Q2 | Q3 | Q4 | Q5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Point | 15 | 20 | 15 | 15 | 35 | 100 |
| Grade |  |  |  |  |  |  |

Good Luck!

Q1) 15 points Ch1 Introduction

What are the five attributes of a good software product?

Maintainability, reliability, security, efficiency, and safety

Q2) 20 points Ch2 SDLC Models

What is the rapid application development (RAD) model? (5 points)

RAD model is a software development life cycle model aiming to develop software products rapidly. It uses iterative prototyping, user feedback, and parallel development of functional modules.

What are the four phases of RAD model? (5 points)

Requirements planning (understand business needs), User design (understanding of users’ requirements by prototyping), Software product construction (development, unit testing, integration, system testing), and Cutover (product transition)

What are the three RAD model benefits? (5 points)

Production time, costs, and risk of failure decrease

What are the three RAD model deficiencies? (5 points)

Lack of documentation, customer shall be involved in the process, poor design

Q3) 15 points Ch3 Requirements Engineering

What are the five ways of writing software requirements?

Natural language (NL), structured NL, design description language, graphical diagrams, mathematical description

Q4) 15 points Ch4 Project Management

What are the five types of risks?

Organizational, technological, process, product, and people

Q5) 35 points Ch5 Project Planning and Scheduling

For the given in the table below set of the seven tasks T1..T7

| Task | Duration (work days) | Dependencies |
| --- | --- | --- |
| T1 | 5 |  |
| T2 | 10 | T1 (M1) |
| T3 | 20 |  |
| T4 | 15 | T1(M1) |
| T5 | 15 | T2, T3 (M2) |
| T6 | 10 | T1, T3 (M3) |
| T7 | 25 | T5, T6 (M4) |

- Explain the meaning of the table and draw respective activity network diagram for the tasks T1..T7 and milestones Start, M1..M4, and Finish (5 points)

The table specifies tasks to be done, their duration in working days, and dependencies in the form (tasks, milestone), where all the TASKS shall complete, and only then respective task (in the same row) can start. The event of finishing of the TASKS is identified as MILESTONE. For example, T7 can start only after completion of T% and T6, which is related to the milestone M4.

16.04            5                  24.04                    20      18.05                                      20.07

25

18.05            10                            12.06

15                   10

15

- Using Turkish calendar-2026 and assuming that the project starts by April, 16, 2026, for each milestone define the date of its reaching. (14 points) When will the project complete? (1 point) Explain your answers

Milestones are marked in the network diagram above: Start 16.04; M1 24.04; M2 18.05; M3 18.05; M4 12.06; Finish 20.07. The project expects finished by 20.07.2026. Tasks are marked by their durations.

- Assuming, there are three engineers, Ali, Bob, and Alice, draw a staff allocation chart for the project (15 points)

| Ali | T1, 16-22.04 | T4, 24.04-15.05 | T5, 18.05-11.06 | T7, 12.06-17.07 |
| --- | --- | --- | --- | --- |
| Bob | T3, 16.04-15.05 |  | T6, 18.05-04.06 |  |
| Alice |  | T2, 24.04-08.05 |  |  |

Detailed staff allocation, tasks are shown by their numbers, holidays are highlighted

| Date | 16. 04 | 17. 04 | 18. 04 | 19. 04 | 20. 04 | 21. 04 | 22. 04 | 23. 04 | 24. 04 | 25. 04 | 26. 04 | 27. 04 | 28. 04 | 29. 04 | 30. 04 | 01. 05 | 02. 05 | 03. 05 | 04. 05 | 05. 05 | 06. 05 | 07. 05 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ali | 1 (5 days) |  |  |  |  |  |  |  | 4 (9 days) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bob | 3 (14 days) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alice |  |  |  |  |  |  |  |  | 2 (9 days) |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Date | 08. 05 | 09. 05 | 10. 05 | 11. 05 | 12. 05 | 13. 05 | 14. 05 | 15. 05 | 16. 05 | 17. 05 | 18. 05 | 19. 05 | 20. 05 | 21. 05 | 22. 05 | 23. 05 | 24. 05 | 25. 05 | 26. 05 | 27. 05 | 28. 05 | 29. 05 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ali | 4 (6 days), totally 15 days |  |  |  |  |  |  |  |  |  | 5 (6 days) |  |  |  |  |  |  |  |  |  |  |  |
| Bob | 3 (6 days), totally 20 days |  |  |  |  |  |  |  |  |  | 6 (6 days) |  |  |  |  |  |  |  |  |  |  |  |
| Alice | 2 (1 day), totally 10 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Date | 30. 05 | 31. 05 | 01. 06 | 02. 06 | 03. 06 | 04. 06 | 05. 06 | 06. 06 | 07. 06 | 08. 06 | 09. 06 | 10. 06 | 11. 06 | 12. 06 | 13. 06 | 14. 06 | 15. 06 | 16. 06 | 17. 06 | 18. 06 | 19. 06 | 20. 06 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ali |  |  | 5 (9 days), totally 15 days |  |  |  |  |  |  |  |  |  |  | 7 (6 days) |  |  |  |  |  |  |  |  |
| Bob |  |  | 6 (4 days), totally 10 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Date | 21. 06 | 22. 06 | 23. 06 | 24. 06 | 25. 06 | 26. 06 | 27. 06 | 28. 06 | 29. 06 | 30. 06 | 01. 07 | 02. 07 | 03. 07 | 04. 07 | 05. 07 | 06. 07 | 07. 07 | 08. 07 | 09. 07 | 10. 07 | 11. 07 | 12. 07 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ali | 7 (15 days), totally 21 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bob |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Date | 13. 07 | 14. 07 | 15. 07 | 16. 07 | 17. 07 | 18. 07 | 19. 07 | 20. 07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ali | 7 (4 days), totally 25 days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bob |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |