## Sheet1
| Task Name | Duration | Pred | relation
1 | New Product Launch
2 | Read the note for an explanation of the purpose of this template | 0 days
3 | Phase 1 - Planning
4 | Identify the launch team | 1 day | 2 | fs
5 | Determine sales objectives | 2 days | 4 | fs
6 | Define launch goals | 5 days | 5 | fs
7 | Determine partners | 3 days | 6 | fs
8 | Establish Launch Budget | 2 days | 7 | fs
9 | Planning COMPLETE | 1 day | 8 | fs
10 | Phase 2 - Initiation
11 | Kickoff product launch | 2 days | 9 | fs
12 | Marketing | 5 days | 11 | fs
13 | Engineering | 8 days | 11 | fs
14 | Manufacturing | 12 days | 13 | fs
15 | Sales | 7 days | 14 | ss + 2 days
16 | Product Support | 5 days | 14, 15 | fs
17 | Field Service | 2 days | 16 | fs
18 | Obtain approval | 1 day | 17,12 | fs
19 | Initiation Phase COMPLETE | 0 days | 18
20 | Phase 3 - Execution of prototype
21 | Marketing | 25 days | 19 | fs
22 | Engineering | 30 days | 19,21 | fs,ss
23 | Manufacturing | 55 days | 22 | fs
24 | Sales | 25 days | 23 | fs
25 | Product Support | 10 days | 24 | fs
26 | Field Service | 3 days | 25 | fs
27 | Prepare for Manufacturing Release | 2 days | 26 | fs
28 | Execution Phase COMPLETE | 0 days | 27 | fs