E-Commerce For Online Medicine Shopping

FINAL REPORT

CMSE 312

PROJECT NO    : 1

GROUP NO    : 1

PROJECT NAME    :e-Commerce For Online Medicine Shopping

PROJECT START DATE   :

PROJECT END DATE    : 18.05.2020

SUPERVISOR    : Assoc. Prof. Dr. Duygu Çelik Ertuğrul

SEMESTER TERM    : Spring 2020

Computer Engineering Department

Eastern Mediterranean University

Term: Spring 2020

# ABSTRACT

This final report is written for the purpose of providing a detailed information about e-Commerce for Online Medicine Shopping System that we have developed through out this 3 month period. Our team is consisting of 4 people : Selin Acan being the project manager and system analyst, Hüseyin Erdağlı being the database developer, Berk Çetin being Programmer and Tester and Samet Alemdaroğlu being the User Interface Designer. The system is a simple implementation of a medicine market where it makes it possible for the users to conduct many pharmacutical operations like drug and item deliverices as well as online doctor consultations and simple diagnostics through chat pannels. The principle objective of this project is to make all these real life operations online and more convenient making it easier to access to a larger range of people.Also since everything will be online, it will create a large experimental resource database where researches may be able to collect important data related with their fields when needed if allowed by governments. Of course there exists some ethical and governmental bylaws that we have followed, which in deed result in some restrictions and limitations of operations that each user may conduct. We also believe that economically this project will bring a new horizon and will have the potential to compete with other similar products.The methods employed through out the project consists of : For the software planning and analysis stage we will conduct meetings and interviews with end users and experts of the area as well as doing online research about the field and analyzing similar systems that currently presented in the market. All the necessary scheduling will be documented using MS Project. For the design stage, we will use tools like Modelio and draw.io to implement necessary diagrams that will also lead the development team in the coding stage.For the coding stage we will use different languages like HTML, CSS, JavaScript and PHP to implement the requested functionalities and requirements and for the database system that will keep the user records will require some SQL tools like mySQL.For the testing stage which will be implemented concurrently with the coding stage we will use well-known testing tools, to reach and cover more test cases in a more time efficient way. We will also consider unique cases observed in the domain that might have catastrophic effects on the application. In the end we obtained a well structured Planning, SRS and SDS document which every stakeholder may benefit and produced a software application which satisfies everything listed in this final report. We consider this project as a success since we were able to prepare and present every document and deliverable in correct time, without any penalties and in the requested way.

Keywords: PHP, JavaScript, Medicine, Shopping, Drug, Diagnosis, HTML, Patient, Doctor, Pharmacy Companies, Research

# Table of Contents

ABSTRACT	II

Table of Contents	III

LIST OF FIGURES	V

LIST OF TABLES	VI

1. INTRODUCTION	1

2. PROJECT PLANNING AND MANAGEMENT	2

3. REQUIREMENTS ANALYSIS	3

3.1 Functional Requirements	3

3.2 Non-Functional Requirements	3

3.3 Realistic constraints	3

3.4 Ethical issues	3

4. DESIGN	4

4.1 High level design (architectural)	4

4.2 Software design	4

5. IMPLEMENTATION	5

5.1 Tools, technologies and platforms used	5

5.2 Algorithms	5

5.3 Standards	5

6. TESTING	6

7. USER GUIDE OF THE SYSTEM	7

8. DISCUSSION	8

9. CONCLUSION	9

10. REFERENCES	10

APPENDICES	11

A.  Instructions for installing the system	11

B.  Code for the system	11

C. Other relevant material	11

# LIST OF FIGURES

- Figure 1 : Work Break Down Structure (WBS)

- Figure 2 : Gantt Chart

- Figure 3 : Network Diagram

- Figure 4 : System Architecture Diagram

- Figure 5 : Context Diagram

- Figure 6 : Level-0 Data Flow Diagram

- Figure 7 : Level-1 Data Flow Diagram 1

- Figure 8 : Level-2 Data Flow Diagram 1

- Figure 9 :  Level-1 Data Flow Diagram 2

- Figure 10 : Level-2 Data Flow Diagram 2

- Figure 11 : Use-Case Diagram

- Figure 12 : Sequence Diagram For Pharmacy Companies 1

- Figure 13 : Sequence Diagram For Pharmacy Companies 2

- Figure 14 : Sequence Diagram For Doctor 1

- Figure 15 : Sequence Diagram For Doctor 2

- Figure 16 : Sequence Diagram For Patient 1

- Figure 17 : Sequence Diagram For Patient 2

- Figure 18 : Sequence Diagram For Admin 1

- Figure 19 : Sequence Diagram For Admin 2

- Figure 20 : Business Process Modeling

- Figure 21 : E-R Diagram

- Figure 22 : Physical Database Tables

- Figure 23 : Activity Diagram

# LIST OF TABLES

- Table   1:  Resource Leveling Matrices

- Table   2:  Project Team Information

- Table   3: Project Packages Tables

- Table   4: Milestones

- Table   5: Procurement Tables

- Table   6: Project Economic Expectation

- Table   7: Instrument/Equipment/Software/Release Purchases

- Table   8:Quarterly Estimated Cost Form

- Table   9: PERT Analysis

- Table   10: PERT Calculation

- Table   11: PERT Results

- Table   12:Unadjusted Function Points Calculation

- Table   13: Technical Complexity Factor Calculation

- Table   14: Probabilities Of Finishing

- Table   15: Crashing Costs

# 1. INTRODUCTION

This project is based on designing and implementing an  online webpage providing medical service to the customers based on their health issues . The main objective of the site is to make medical service accessible to the people all around the world eliminating constraints like reachability issues from less developed countries, deficiencies in cash-transactions and inaccurate and time consuming operations due to the problems in  non-automated healthcare systems. Our goal is to increase customer satisfaction, minimize human-related errors by reducing the man power needed and provide a new system that is efficient to operate, secure and maintainable.

The main purpose of this system is to  provide healthcare to a much larger area of people than we reach today with the current systems. While putting extra stress on customer information security and using this information to provide personalized service to each specific customer, we hope that people can get the most beneficial service without waiting being serviced physically. Also this system will reduce the amount of  heavy work expected from people working in the medical field and hence increase the efficiency of both people and accuracy of the services. Since it is an application operating on the system and not an actual person, every customer will be treated as equal and get the same opportunities with everyone else. With the help of this evidence-based portable system, costumers will be able to benefit so much more than the old systems.

We have conducted some domain and market analysis based on the health-care applications. As a result of these information collection processes, we come to the conclusion that although there exists medicine shopping systems currently in the software market that serves a huge range of people, they are either not enough to reach a wide variety and number of customers by limiting the region they provide service to, or they have some accuracy issues when doing diagnostics or suggesting the right drug and treatment due to the inconsistencies with their data sets. Also payment, timing and product transportation was another issue faced by the end-users of similar systems. Depending on these reasons we decided that this kind of popular application should not continue executing like this but better needs an improvement, an increase in user satisfaction and additional functionalities that people can benefit.

This version of the system will be suitable for small firms and corporations who would like to make an investment and enlarge their coverage cells. The system will be designed for the use of many national and international companies cooperating with a wide variety of doctors and pharmacists and hence will simulate a medicine market. Because of this reason, the system may attract the attention of healthcare organizations or governments who would like to improve their current systems.

# 2. PROJECT PLANNING AND MANAGEMENT

Through out the whole project we followed the principles and life cycle indicated in our Project Planning and Management Report. There were no major changes in our implementation.

WBS For e-Commerce For Online Medicine Shopping Project :

Fig 1. Work Break Down Structure (WBS)

The more detailed WBS is included using MS Project in the below sections identifying the tasks that we performed.

Resource Leveling (Resource Matrices) :

| Role Activity | Project Manager | System Analyst | Programmer | Tester | Database Developer | User Interface Designer |
| --- | --- | --- | --- | --- | --- | --- |
| Project Initiation Activities | x | x | x | x |  |  |
| Project Planning Activities | x | x | x | x |  |  |
| Project Design Activities | x | x | x | x | x |  |
| Project Code Development | x |  | x |  | x | x |
| Project Testing | x |  | x | x | x | x |
| Maintanance Activities | x | x | x | x | x | x |
| Project Closure | x | x |  |  |  |  |

Table 1. Resource Leveling Matrice

2.1 Preliminary Project Information

Project Information

| Project No | 1 |
| --- | --- |
| Project Name | E-Commerce For Online Medicine Shopping |
| Start Date | 4th March, 2020 |
| End Date | 3rd June, 2020 |
| Time | 3 months |

# Team Information

| Project Manager |  |  |  |
| --- | --- | --- | --- |
| Name Surname |  | ID No |  |
| Title/Role | Project Manager, System Analyst |  |  |
| Address | Famagusta |  |  |
| Phone |  |  |  |
| Email |  |  |  |

| Student 1 |  |  |  |
| --- | --- | --- | --- |
| Name Surname |  | ID No |  |
| Title/Role | Database Developer |  |  |
| Address | Famagusta |  |  |
| Phone |  |  |  |
| Email |  |  |  |

| Student 2 |  |  |  |
| --- | --- | --- | --- |
| Name Surname |  | ID No |  |
| Title/Role | Programmer,Tester |  |  |
| Address | Famagusta |  |  |
| Phone |  |  |  |
| Email |  |  |  |

| Student 3 |  |  |  |
| --- | --- | --- | --- |
| Name Surname |  | ID No |  |
| Title/Role | User Interface Designer |  |  |
| Address | Famagusta |  |  |
| Phone |  |  |  |
| Email |  |  |  |

# Table 2. Project Team Information

2.2 Aim, Purpose and Target Users

The main idea of developing a web-based medical application is to provide accessibility to the customer’s all around the world including the countries that lack in healthcare services, anytime through out the day with high quality work and delivery that best meets their personal needs. We aim to achieve a decrease in the intensive labor and pressure on the health-care workers as well as increasing accuracy, reliability, delivery speed and maintainability of our service and products by eliminating the side effects that may rise up from the hard working conditions that in the end result in providing robustness . Our goal is to develop a system that is more than adequate and highly beneficial for the  customers both in a functional and financial way. Since we are working with highly private customer information, it is a high priority for us to keep the system secure and thread-free. Although some similar systems currently exist in the software market, we believe that our product can take it into one step further and bring a new perspective and alternative to the common understanding of medical software products.

The allure and superiority of our system is coming from the reliable shipping facilities and personalized medical services at the comfort of your own home. The system interface will have a user-friendly application where people from any age can easily use while preserving the site aesthetics that will attract the eye. The common insufficient features will be eliminated as much as possible and the end product will be able to compete at global standards.  The confidentiality, integrity and availability of the system will be kept as a high priority in our system which will bring a significant advantage for our project. As our main goal is to increase accessibility, we will also put stress on portability issues that bring the end product to the next level.

As described in the introduction section of this report the system will be suitable for small firms and corporations who would like to make an investment and enlarge their coverage cells. The system will be designed for the use of many national and international companies cooperating with a wide variety of doctors and pharmacists and hence will simulate a medicine market. Because of this reason, the system may attract the attention of healthcare organizations or governments who would like to improve their current systems.

2.3 The Reason For Starting This Project

The primary reason on accepting to start this project is that our team has a huge interest in the improvements and developments made in medical area. We had an overall understanding of the problem domain and having the chance to implement our knowledge on a practical form was an opportunity we did not want to miss. On the other hand, medicine is an immense and endless field which is open to any kind of advancement especially including the ones in software related areas. Although there exists many medical and health related applications in the market, it would be absurd and meaningless to claim that everything is perfectly working and there is no room for any other product. Also as mentioned above, the currently presented ones are not bug-free and are not enough to provide all customer needs and requirements as a result of many restrictions and ethical issues. Taking in to consideration all of these things mentioned above we decided to select this topic and start this project.

2.4 Output/Success Criteria

We will accept that our product finalized successfully and served its purpose if and only if all user requirements are perfectly satisfied and implemented in our code and presented in the execution of our product. We also consider issues in the practical field whether it made it easy for the users to perform their daily actions and jobs, whether it made medical material production and delivery such as drugs and equipments convient and whether it helped researches and diagnostics in medical field. Once these issues are covered, we can claim that our product guarantees a high quality execution and succefull completion.

2.5 Gantt Chart

Fig2. Gantt Chart

2.6 Project Package Tables

| Work Package No | 1 |
| --- | --- |
| Work Package Name | Project Feasibility and Pre-Research (Feasibility Analysis) |
| Start-End Date and Time | 4.3.2020-13.3.2020 |
| Related Organizations | - |

1- List the activities of work packages.

1.1 Project Process and Economic Feasibility: - Market Research to find check similar systems and analyse the potential need to this system. - Determining the general structure of the system in order to have a proper idea of its benefits and costs . - Analysing possible risks - Calculating the needed fund for the desired project. - Estimating revenue and expense for this project . - Deciding whether the project economically sustainable and profitable for our team. 1.2 Technological Feasibility: - Deciding technical infrastructure needed to conduct the project. - Deciding if we have the appropriate environment for the system (Web-based) and compatibility issues (for pc and mobile devices.). If we don’t have enough technology at the moment, analyse the market to see if obtaining these resources and adding additional costs will decline the project benefits.

2- Describe the methods and parameters that will be used for work package.

In order to achieve a functional and sustainable Online Medicine Shopping system, in-depth analysis of similar systems, interviews with possible stakeholders (pharmacies, doctors, banks, and patents) would be carried out by all group members to make them familiar with all parts of the system. MS Project will be used to perform this stage.

3- List the experiments, tests and analysis in the work package.

- Research and analyzing similar systems - Revenue and expense estimation - Risk estimations. - Selection of experienced group members and deciding on work distribution - Interview with possible users for better requirement specification

4- List the output of work package and its success criterias.

Outputs: - Establishing the distribution of tasks. - Having an idea about similar projects and systems. - Understanding the general idea of the Medicine Shopping system. - The decision on whether to move forward with the project or leave it - Estimation on profits and costs Success Criterias: - Making team members familiar with the project. - Having idea about the overall view of the system and concepts. - Better understanding the required requirements. - Deciding if the project is profitable or not. - Understanding the possible risks that may occur in the system.

5- Explain the relation of output with other work packages

This work package is the basic step to perform other work packages as the others will developed according to this one. It will give an estimation on whether the project will succeed if certain steps are performed.

| Work Package No | 2 |
| --- | --- |
| Work Package Name | Based System Design Technology (Analysis & Design stage) |
| Start-End Date and Time | 16.3.2020-20.3.2020 |
| Related Organizations | - |

1- List the activities of work packages.

- Define stakeholders for the system - Determine necessary requirements for the system - Determining resources needed for the system (workers, machines, tools, computers, etc.) - Defining the relations between stakeholders - Maintaining team members and work description - Drawing necessary diagrams to make implementation clearer.

2- Describe the methods and parameters that will be used for work package.

- Dividing the team members into small groups - Incremental Modelling and other universally accepted diagrams - Prototype Methodology

3- List the experiments, tests and analysis in the work package.

- Create overview of general flow of the system for better designing - Gathering more design ideas from the divided teams by interviews and researches - Creating samples

4- List the output of work package and its success criterias.

Outputs: - Compatible requirements reports - Some design samples of the system - Detailed models which shows the overall flow of the system Success Criterias: - Understanding system structure - Coming up with solutions to the possible risks of the system

5- Explain the relation of output with other work packages

This system will use the feasibility and requirements analysis package as an input to perform the diagraming and further analysis and change and risk management implementations for the requested business operations. The output of this phase will be used as an input on the coding stage ( Development of System Software ) .

| Work Package No | 3 |
| --- | --- |
| Work Package Name | Development of System Software (Development Stage) |
| Start-End Date and Time | 23.3.2020-25.5.2020 |
| Related Organizations | - |

1- List the activities of work packages.

- Design and develop a friendly User Interface - Develop Database for storing data - Programming of the system - Implementing requirements to the system

2- Describe the methods and parameters that will be used for work package.

- mySQL for database (storing data) - HTML to create the main structure of the system - CSS for styling the system - JavaScript to make system functional and more dynamic - PHP to connect the system to database.

3- List the experiments, tests and analysis in the work package.

- Checking compatibility of requirements - Checking functionability of the system - Develop enough amount of storage - Analysing algorithms if there are unnecessary codes

4- List the output of work package and its success criterias.

Outputs: - Ready and functional sample of system - Available for testing the system Success Criterias: - Minimum risk of errors - Well codded system and designed database - Well designed and friendly user interface

5- Explain the relation of output with other work packages

At the end of this work package we will have a functional prototype of the system and the user interface which represents all requirements. After this work packages we will be ready to perform various test to the system to see if there is any error or mistakes. It will be used as input to the testing team. It will also use the design and requirements packages as input to gather the required functionalities in a correct and complete form.

| Work Package No | 4 |
| --- | --- |
| Work Package Name | Prototype Implementation and Test Study and Maintenance (Test & Maintenance stage) |
| Start-End Date and Time | 25.5.2020-3.6.2020 |
| Related Organizations | - |

1- List the activities of work packages.

- Security testing - Penetration testing - Path testing - Performance testing

2- Describe the methods and parameters that will be used for work package.

- Black-box and white-box penetration tests for security - User acceptance testing for requirements - Model-based testing - Unit testing

3- List the experiments, tests and analysis in the work package.

- Black-box and white-box testing will simulate an external hacking attack - Model-based testing will represent whether the system performs the desired behaviour - Unit testing will check the design and behaviour of the applications and make sure that they are working as desired

4- List the output of work package and its success criterias.

Outputs: - Results and reports of the tests - Error reports Success Criterias: The system and its applications performed and behave as desired and ready to use

5- Explain the relation of output with other work packages

If this work package is completed well and without any problems, this means the system is work perfectly, there is no error or any problems and it behaves as desired so it is ready to use. This package will be implemented right after the coding stage in each cycle iteratively. The test results will be stored for future implementation and documentation purposes.

Table 3. Project Package Tables

2.7 Milestones

|  | Description of Output | Expected Time Interval |
| --- | --- | --- |
| 1 | Project Feasibility and Pre-Research (Feasibility Analysis) | 4.3.2020-13.3.2020 |
| 2 | Based System Design Technology (Analysis & Design stage) | 16.3.2020-20.3.2020 |
| 3 | Development of System Software (Development Stage) | 23.3.2020-25.5.2020 |
| 4 | Prototype Implementation and Test Study and Maintenance (Test & Maintenance stage) | 25.5.2020-3.6.2020 |
| 5 | Project Closure | 3.6.2020 |

Table 4. Milestones

2.8 Procurement Tables

| Risk | Probability | Effects | Your Strategy |
| --- | --- | --- | --- |
| The budget required for the software may not be calculated in detail. | High | Serious | Investigate the budget that is needed to develop this software; Add additional cost to the software documentation. |
| The database may give an unexpected connection error. | High | Serious | Use database servers dynamically located in different data centers. |
| Some software developers may need to leave from the team. | Moderate | Tolerable | Hire a new developer who knows the appropriate features of the software. |
| Continuous change in the requirements by the customer company | High | Tolerable | Replace potentially defective components with more reliable bought-in components. |
| Test case results may be inefficient and not enough to market the software. | High | Serious | Research the test cases using different tester team to analyze the cases better |
| Third party software integrations may cause some efficiency problems. | Moderate | Serious | Deal with 3rd party software companies. |
| No advanced technology available or the existing technology is in the initial stages. | High | Serious | Buy all the devices and items needed to develop software beforehand or change the dependent requirements accordingly. |
| Lack of product information and some significant requirements | Moderate | Serious | Include the identified important missing requirements to the software document. |
| Government rule changes. | High | Serious | Agree with the government or remove inappropriate requirements. |

Table 5. Procurement Table

2.9 Commercialization Potential

Today many industries use recognized financial practices such as NPV to guide decisions on whether to pursue commercialization of a new technology. The same strategies can be appllied to this project.When releasing this project to the software market, our initial goal is to make healthcare accessible to everyone around the world. If this project is to be commercialized, this may result in producing more ways of reaching various drug companies and enlarging our service range which in the end this advantage may translate into significant financial or operational benefits. If this project is commercialized and grow into a much larger version of itself, it may effect the income distribution emerge from healthcare market activity. This project may also introduce concepts like pre-paid care. The risks that may arise from the commercialization of this project is that the difference between poor and non-poor is not always clear or stable and this may lead to actually eliminating some people that actually need help. A fake prescription event can be given as another example to the possible risks in the system.

2.10 Project Economic Expectation

| 2- List your expectations to your team which are come by your project |  |
| --- | --- |
| Time-to-market (month): | 10 months |
| The expected increase in sales revenue (%): | %10 |
| The expected increase in market share (%): | %10 |
| Time to start to gain: | 15 months |

Table 6. Project Economic Expectation

2.11 Instrument / Equipment / Software / Release Purchases

Table 7. Instrument / Equipment / Software / Release Purchases

2.12 Quarterly Estimated Cost Form

Table 8. Quarterly Estimated Cost Form

2.13 Pert Analyzing & Crashing Analyzing

From MS Project:

| Task ID | Task Name | Expected Duration | Dependency | Probability of Sucessful Completion Rate Of Each Path ( % ) |
| --- | --- | --- | --- | --- |
| A | Initiating the Project | 1 day | - | 99 |
| B | Market analysis to observe if there is a need to this system | 1 day | A | 98 |
| C | Market analysis to compare similar systems | 2 day | A | 98 |
| D | Economic feasiblity estimations | 1 day | A | 85 |
| E | Technological feasibility estimations | 2 days | A | 85 |
| F | Interviewing Stakeholders and requirements collection | 3 days | B,C,D,E | 90 |
| G | Estimating revenue and expenses | 2 day | F | 85 |
| H | Constructing the work breakdown | 1 day | F | 90 |
| I | Decision on performing the project or not | 1 day | G,H | 95 |
| J | Drawing diagrams based on the requirements | 5 days | I | 90 |
| K | Determining the resources needed from the system | 2 days | I | 90 |
| L | Determining the system parameters | 2 days | J,K | 90 |
| M | Discussions on system design | 2 day | L | 99 |
| N | Classification of the attributes for database | 2 days | M | 90 |
| O | Building the query model for database | 3 days | N | 90 |
| P | Entering system data for database | 3 days | O | 90 |
| R | Creating algorithms for coding | 12 days | P | 90 |
| S | Implementing user functionality for coding | 12 days | R | 90 |
| T | Connecting system to the database for coding | 5 days | S | 90 |
| U | Styling the system | 5 days | T | 90 |
| V | Improving the system to make it more dynamic | 3 days | U | 90 |
| W | Security testing | 2 days | V | 95 |
| X | Penetration testing | 2 days | V | 95 |
| Y | Path testing | 2 days | V | 95 |
| Z | Performance testing | 4 days | V | 95 |
| ZZ | Closure of the project | 2 day | Z | 95 |

Table 9. PERT Analysis Table

Network Diagram (Indicating the Critical Path With Red Lines)

Fig.3 Network Diagram

CPM (Critical Path Management) Analysis By Using PERT (Defining Paths)

The first one with bold font is our critical path having  days. The calculation of the first path is shown,  other paths are calculated in the similar way by checking the table values in PERT Calculation Section.

PERT CALCULATION

Expected time calculated using expected duration values.Variance calculated by variance values of each process. Standart deviation calculated by taking square root of variance.You can also see all other possible paths.The longest path “ACFGIJLMOPR S T U V Z ZZ” indicated in bold color which has 67.4853 days is our critical path.

Table 10. PERT Calculation

|  | Paths | Total Expected Time For Each Path | Variance Of Each Path | Standart Deviation Of Each Path |
| --- | --- | --- | --- | --- |
| 1 | A E F H I J L M N O P R S T U V Z ZZ | 1.083+2+3+1.083+1.083+4.833+2+2+2+3.16+3+11,33+11,33+5+4,833+3+3,833+2=65.482 | 0.0625+ 0.111+0.111+0..0625+0.0625+0.25+0.111+0.111+0.111+0.25+0.111+2.777+2.777+0.444+0.6944+0.111+0.25+0.111= 8.5179 | 8.5179= 2.918544158 |
| 2 | A B F G I J L M N O P R S T U V W ZZ | 64.9023 | 8.7905 | 2.9648 |
| 3 | A B F G I J L M N O P R S T U V X ZZ | 64.9023 | 8.7905 | 2.9648 |
| 4 | A B F G I J L M N O P R S T U V Y ZZ | 64.9023 | 8.7905 | 2,9648 |
| 5 | A B F G I J L M N O P R S T U V Z ZZ | 66.7353 | 8.9305 | 2,9883 |
| 6 | A C F G I J L M N O P R S T U V W ZZ | 65.6523 | 8.7269 | 2,9541 |
| 7 | A C F G I J L M N O P R S T U V X ZZ | 65.6523 | 8.7269 | 2,9541 |
| 8 | A C F G I J L M N O P R S T U V Y ZZ | 65.6523 | 8.7269 | 2,9541 |
| 9 | A C F G I J L M N O P R S T U V Z ZZ | 67.4853 | 8.8669 | 2,9773 |
| 10 | A D F G I J L M N O P R S T U V W ZZ | 64.7356 | 8.6794 | 2,,9460 |
| 11 | A D F G I J L M N O P R S T U V X ZZ | 64.7356 | 8.6794 | 2,9460 |
| 12 | A D F G I J L M N O P R S T U V Y ZZ | 64.7356 | 8.6794 | 2,9460 |
| 13 | A D F G I J L M N O P R S T U V Z ZZ | 66.5686 | 8.8194 | 2,9697 |
| 14 | A E F G I J L M N O P R S T U V W ZZ | 65.6523 | 8.7269 | 2,9541 |
| 15 | A E F G I J L M N O P R S T U V X ZZ | 65.6523 | 8.7269 | 2,9541 |
| 16 | A E F G I J L M N O P R S T U V Y ZZ | 65.6523 | 8.7269 | 2,9541 |
| 17 | A E F G I J L M N O P R S T U V Z ZZ | 67.4853 | 8.8669 | 2,9773 |
| 18 | A B F H I J L M N O P R S T U V W ZZ | 63.9853 | 8.743 | 2,9568 |
| 19 | A B F H I J L M N O P R S T U V X ZZ | 63.9853 | 8.743 | 2,9568 |
| 20 | A B F H I J L M N O P R S T U V Y ZZ | 63.9853 | 8.743 | 2,9568 |
| 21 | A B F H I J L M N O P R S T U V Z ZZ | 65.8183 | 8.883 | 2,9804 |
| 22 | A C F H I J L M N O P R S T U V W ZZ | 64.7353 | 8.6794 | 2,9460 |
| 23 | A C F H I J L M N O P R S T U V X ZZ | 64.7353 | 8.6794 | 2,9460 |
| 24 | A C F H I J L M N O P R S T U V Y ZZ | 64.7353 | 8.6794 | 2,9460 |
| 25 | A C F H I J L M N O P R S T U V Z ZZ | 66.5683 | 8.8194 | 2,9697 |
| 26 | A D F H I J L M N O P R S T U V W ZZ | 63.8186 | 8.6319 | 2,9380 |
| 27 | A D F H I J L M N O P R S T U V X ZZ | 63.8186 | 8.6319 | 2,9380 |
| 28 | A D F H I J L M N O P R S T U V Y ZZ | 63.8186 | 8.6319 | 2,9380 |
| 29 | A D F H I J L M N O P R S T U V Z ZZ | 65.6516 | 8.7719 | 2,9617 |
| 30 | A B F G I K L M N O P R S T U V W ZZ | 62.0663 | 8.4005 | 2,8983 |
| 31 | A B F G I K L M N O P R S T U V X ZZ | 62.0663 | 8.4005 | 2,8983 |
| 32 | A B F G I K L M N O P R S T U V Y ZZ | 62.0663 | 8.4005 | 2,8983 |
| 33 | A B F G I K L M N O P R S T U V Z ZZ | 63.8993 | 8.5405 | 2,9224 |
| 34 | A C F G I K L M N O P R S T U V W ZZ | 62.8163 | 8.3369 | 2,8873 |
| 35 | A C F G I K L M N O P R S T U V X ZZ | 62.8163 | 8.3369 | 2,8873 |
| 36 | A C F G I K L M N O P R S T U V Y ZZ | 62.8163 | 8.3369 | 2,8873 |
| 37 | A C F G I K L M N O P R S T U V Z ZZ | 64.6493 | 8.4769 | 2,9115 |
| 38 | A D F G I K L M N O P R S T U V W ZZ | 61.8996 | 8.2894 | 2,8791 |
| 39 | A D F G I K L M N O P R S T U V X ZZ | 61.8996 | 8.2894 | 2,8791 |
| 40 | A D F G I K L M N O P R S T U V Y ZZ | 61.8996 | 8.2894 | 2,8791 |
| 41 | A D F G I K L M N O P R S T U V Z ZZ | 63.7326 | 8.4294 | 2,9033 |
| 42 | A E F G I K L M N O P R S T U V W ZZ | 62.8163 | 8.3369 | 2,8873 |
| 43 | A E F G I K L M N O P R S T U V X ZZ | 62.8163 | 8.3369 | 2,8873 |
| 44 | A E F G I K L M N O P R S T U V Y ZZ | 62.8163 | 8.3369 | 2,8873 |
| 45 | A E F G I K L M N O P R S T U V Z ZZ | 64.6493 | 8.4769 | 2,9115 |
| 46 | A B F H I K L M N O P R S T U V W ZZ | 61.1493 | 8.353 | 2,8901 |
| 47 | A B F H I K L M N O P R S T U V X ZZ | 61.1493 | 8.353 | 2,8901 |
| 48 | A B F H I K L M N O P R S T U V Y ZZ | 61.1493 | 8.353 | 2,8901 |
| 49 | A B F H I K L M N O P R S T U V Z ZZ | 62.9823 | 8.493 | 2,9142 |
| 50 | A C F H I K L M N O P R S T U V W ZZ | 61.8993 | 8.2894 | 2,8791 |
| 51 | A C F H I K L M N O P R S T U V X ZZ | 61.8993 | 8.2894 | 2,8791 |
| 52 | A C F H I K L M N O P R S T U V Y ZZ | 61.8993 | 8.2894 | 2,8791 |
| 53 | A C F H I K L M N O P R S T U V Z ZZ | 63.7323 | 8.4294 | 2,9033 |
| 54 | A D F H I K L M N O P R S T U V W ZZ | 60.9826 | 8.2419 | 2,8708 |
| 55 | A D F H I K L M N O P R S T U V X ZZ | 60.9826 | 8.2419 | 2,8708 |
| 56 | A D F H I K L M N O P R S T U V Y ZZ | 60.9826 | 8.2419 | 2,8708 |
| 57 | A D F H I K L M N O P R S T U V Z ZZ | 62.8156 | 8.3819 | 2,8951 |
| 58 | A E F H I K L M N O P R S T U V W ZZ | 61.8993 | 8.2894 | 2,8791 |
| 59 | A E F H I K L M N O P R S T U V X ZZ | 61.8993 | 8.2894 | 2,8791 |
| 60 | A E F H I K L M N O P R S T U V Y ZZ | 61.8993 | 8.2894 | 2,8791 |
| 61 | A E F H I K L M N O P R S T U V Z ZZ | 63.7323 | 8.3819 | 2,8951 |

Formulas :

Expected Time: (min. duration +4*avg. duration +max. duration)/6

Variance: ((max. duration-min.duration)/6)2

Derivation: variance

| Task ID | Task Name | Minimum Duration | Average Duration | Maximum Duration | Expected Time | Variance | Standart Deviation | Dependency (Predicate) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Initiating the Project | 0.5 day | 1 day | 2 day | 1.083 day | 0.0625 | 0.25 | - |
| B | Market analysis to observe if there is a need to this system | 0.5 day | 1 day | 3 day | 1.25 day | 0.1736 | 0.4166533331 | A |
| C | Market analysis to compare similar systems | 1 day | 2 day | 3 day | 2 day | 0.1111 | 0.333316662 | A |
| D | Economic feasiblity estimations | 0.5 day | 1 day | 2 day | 1.0833 day | 0.0625 | 0.25 | A |
| E | Technological feasibility estimations | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | A |
| F | Interviewing Stakeholders and requirements collection | 2 day | 3 days | 4 day | 3 days | 0.1111 | 0.333316662 | B,C,D,E |
| G | Estimating revenue and expenses | 1 day | 2 day | 3 day | 2 day | 0.1111 | 0.333316662 | F |
| H | Constructing the work breakdown | 0.5 day | 1 day | 2 day | 1.0833 day | 0.0625 | 0.25 | F |
| I | Decision on performing the project or not | 0.5 day | 1 day | 2 day | 1.08333 day | 0.0625 | 0.25 | G,H |
| J | Drawing diagrams based on the requirements | 3 day | 5 days | 6 day | 4.8333 days | 0.25 | 0.5 | I |
| K | Determining the resources needed from the system | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | I |
| L | Determining the system parameters | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | J,K |
| M | Discussions on system design | 1 day | 2 day | 3 day | 2 day | 0.1111 | 0.333316662 | L |
| N | Classification of the attributes for database | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | M |
| O | Building the query model for database | 2 day | 3 days | 5 day | 3.16667 days | 0.25 | 0.5 | N |
| P | Entering system data for database | 2 day | 3 days | 4 day | 3 days | 0.1111 | 0.333316662 | O |
| R | Creating algorithms for coding | 5 day | 12 days | 15 day | 11.3333 days | 2.7777 | 1.666433317 | P |
| S | Implementing user functionality for coding | 5 day | 12 days | 15 day | 11.3333 days | 2.7777 | 1.666433317 | R |
| T | Connecting system to the database for coding | 3 day | 5 days | 7 day | 5 days | 0.4444 | 0.66633325 | S |
| U | Styling the system | 2 day | 5 days | 7 day | 4.8333 days | 0.694444 | 0.8333330667 | T |
| V | Improving the system to make it more dynamic | 2 day | 3 days | 4 day | 3 days | 0.1111 | 0.333316662 | U |
| W | Security testing | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | V |
| X | Penetration testing | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | V |
| Y | Path testing | 1 day | 2 days | 3 day | 2 days | 0.1111 | 0.333316662 | V |
| Z | Performance testing | 2 day | 4 days | 5 day | 3.8333 days | 0.25 | 0.5 | V |
| ZZ | Closure of the project | 1 day | 2 day | 3 day | 2 day | 0.111 | 0.333316662 | Z |

Table 11. PERT Results

Function Point Calculation

| Functions | Simple No | Simple Weight | Average No | Average Weight |  | Complex No | Complex Weight | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| User Input | 10 | 3 | 5 | 4 | 2 |  | 6 | 10*3+5*4+2*6 =62 |
| User Output | 10 | 4 | 5 | 5 | 2 |  | 7 | 40+25+14=79 |
| User Query | 20 | 3 | 10 | 4 | 1 |  | 6 | 60+40+6=106 |
| Internal Fıles | 30 | 7 | 5 | 10 | 5 |  | 15 | 210+50+75=335 |
| External Interfaces | 30 | 5 | 10 | 7 | 5 |  | 10 | 150+70+50=270 |

Table 12. Unadjusted Function Point Calculation

Total: number*weightfactor= 62+79+106+335+270= 852= Unadjusted Function Points

Technical Complexity Factor (DI)

| Factors | Complexity | Complexity Value |
| --- | --- | --- |
| Data Communication | Essential | 5 |
| Performance Criteria | Essential | 5 |
| Online Data Entry | Significant | 4 |
| Reusability | Significant | 4 |
| Ease of Installation | Essential | 5 |
| Maintainability | Essential | 5 |
| Online Updating | Significant | 4 |
| Complex Calculations | Moderate | 2 |
| Others ( Portability,etc) | Average | 3(*6 of others) |

Table 13. Technical Complexity Factor Calculation

Total DI = 52

Function Points (FP) = UFP*(0.65+0.01*DI)=852*(0.65+0.01*52)=996.84

COCOMO Estimation

We will calculate for JAVA Programming Language :

KLOC from FP = 996.84*53=52832.52 LOC =52.83252 KLOC

Since this project is a well-known type of project, the team is familiar with the methods and languages used, we will follow an organic type of development :

Effort =person-month = a*(KLOC)^b = 2.4*52.831.05= 152.6093

Duration-in-month = c*(person-month)^d= 2.5*152.60930.38=16.8927 months

# of people=Effort/Duration= 152.6093/16.8927= 9.034002606 person required.

Crashing Approach

Z= (specified time – expected time) / path standart deviation

For each path in critical path management section we will calculate the z value :

Assume : We an order came saying that the project should be completed within 60 days instead of 67 days ( Reduction of 1 week ).

| 1 | Expected Time Of The Path | Specified Time | Standart Deviation Of The Path | Z value | Probability Of Finishing |
| --- | --- | --- | --- | --- | --- |
| 2 | 65.482 | 60 | 2.918544158 | (65.482-60)/ 2.9185=1.8783 | 0.96983 |
| 3 | 64.9023 | 60 | 2.9648 | 1.6535 | 0.95089 |
| 4 | 64.9023 | 60 | 2.9648 | 1.6535 | 0.95089 |
| 5 | 64.9023 | 60 | 2,9648 | 1.6535 | 0.95089 |
| 6 | 66.7353 | 60 | 2,9883 | 2.25381 | 0.9879 |
| 7 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 8 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 9 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 10 | 67.4853 | 60 | 2,9773 | 2.5141 | 0.99403 |
| 11 | 64.7356 | 60 | 2,,9460 | 1.6074 | 0.94602 |
| 12 | 64.7356 | 60 | 2,9460 | 1.6074 | 0.94602 |
| 13 | 64.7356 | 60 | 2,9460 | 1.6074 | 0.94602 |
| 14 | 66.5686 | 60 | 2,9697 | 2.2111 | 0.98649 |
| 15 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 16 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 17 | 65.6523 | 60 | 2,9541 | 1.9133 | 0.97215 |
| 18 | 67.4853 | 60 | 2,9773 | 2.5141 | 0.99403 |
| 19 | 63.9853 | 60 | 2,9568 | 1.3478 | 0.91114 |
| 20 | 63.9853 | 60 | 2,9568 | 1.3478 | 0.91114 |
| 21 | 63.9853 | 60 | 2,9568 | 1.3478 | 0.91114 |
| 22 | 65.8183 | 60 | 2,9804 | 1.9521 | 0.97454 |
| 23 | 64.7353 | 60 | 2,9460 | 1.6073 | 0.94601 |
| 24 | 64.7353 | 60 | 2,9460 | 1.6073 | 0.94601 |
| 25 | 64.7353 | 60 | 2,9460 | 1.6073 | 0.94601 |
| 26 | 66.5683 | 60 | 2,9697 | 2.2117 | 0.98651 |
| 27 | 63.8186 | 60 | 2,9380 | 1.2997 | 0.90315 |
| 28 | 63.8186 | 60 | 2,9380 | 1.2997 | 0.90315 |
| 29 | 63.8186 | 60 | 2,9380 | 1.2997 | 0.90315 |
| 30 | 65.6516 | 60 | 2,9617 | 1.9082 | 0.97182 |
| 31 | 62.0663 | 60 | 2,8983 | 0.7129 | 0.76205 |
| 32 | 62.0663 | 60 | 2,8983 | 0.7129 | 0.76205 |
| 33 | 62.0663 | 60 | 2,8983 | 0.7129 | 0.76205 |
| 34 | 63.8993 | 60 | 2,9224 | 1.3342 | 0.90893 |
| 35 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 36 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 37 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 38 | 64.6493 | 60 | 2,9115 | 1.5968 | 0.94484 |
| 39 | 61.8996 | 60 | 2,8791 | 0.659789 | 0.74531 |
| 40 | 61.8996 | 60 | 2,8791 | 0.6597 | 0.74531 |
| 41 | 61.8996 | 60 | 2,8791 | 0.6597 | 0.74531 |
| 42 | 63.7326 | 60 | 2,9033 | 1.2856 | 0.90071 |
| 43 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 44 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 45 | 62.8163 | 60 | 2,8873 | 0.9754 | 0.83532 |
| 46 | 64.6493 | 60 | 2,9115 | 1.5968 | 0.94484 |
| 47 | 61.1493 | 60 | 2,8901 | 0.3976 | 0.65454 |
| 48 | 61.1493 | 60 | 2,8901 | 0.3976 | 0.65454 |
| 49 | 61.1493 | 60 | 2,8901 | 0.3976 | 0.65454 |
| 50 | 62.9823 | 60 | 2,9142 | 1.0233 | 0.84692 |
| 51 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 52 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 53 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 54 | 63.7323 | 60 | 2,9033 | 1.2855 | 0.90069 |
| 55 | 60.9826 | 60 | 2,8708 | 0.3422 | 0.6339 |
| 56 | 60.9826 | 60 | 2,8708 | 0.3422 | 0.6339 |
| 57 | 60.9826 | 60 | 2,8708 | 0.3422 | 0.6339 |
| 58 | 62.8156 | 60 | 2,8951 | 0.9725 | 0.8346 |
| 59 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 60 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 61 | 61.8993 | 60 | 2,8791 | 0.6596 | 0.74524 |
| 62 | 63.7323 | 60 | 2,8951 | 1.2891 | 0.90132 |

Table 14. Probabilities Of Finisihing

Probabilities obtained from the z-table.

So depending on these values assume we want to reduce our project time by 1 week, then :

| Tasks | Normal Time (day) | Crash Time (day) | Normal Cost ($) | Crash Cost ($) | Reduce Cost Per Day ($) |
| --- | --- | --- | --- | --- | --- |
| A | 1 | 2 | 30 | 35 | 5 |
| B | 1 | 2 | 30 | 35 | 5 |
| C | 2 | 3 | 35 | 40 | 5 |
| D | 1 | 2 | 30 | 35 | 5 |
| E | 2 | 3 | 35 | 40 | 5 |
| F | 3 | 4 | 40 | 70 | 30 |
| G | 2 | 3 | 35 | 40 | 5 |
| H | 1 | 2 | 30 | 35 | 5 |
| I | 1 | 2 | 30 | 35 | 5 |
| J | 5 | 7 | 60 | 80 | 10 |
| K | 2 | 5 | 35 | 50 | 5 |
| L | 2 | 4 | 30 | 50 | 10 |
| M | 2 | 3 | 30 | 35 | 5 |
| N | 2 | 6 | 30 | 42 | 4 |
| O | 3 | 8 | 45 | 90 | 9 |
| P | 3 | 6 | 45 | 90 | 15 |
| Q | 12 | 16 | 100 | 160 | 12 |
| R | 12 | 18 | 100 | 160 | 10 |
| S | 12 | 20 | 100 | 140 | 5 |
| T | 5 | 7 | 50 | 58 | 4 |
| U | 5 | 8 | 50 | 71 | 7 |
| V | 3 | 5 | 40 | 50 | 5 |
| W | 2 | 5 | 30 | 60 | 10 |
| X | 2 | 4 | 30 | 38 | 4 |
| Y | 2 | 3 | 30 | 35 | 5 |
| Z | 4 | 8 | 60 | 80 | 5 |
| Zz | 2 | 4 | 30 | 40 | 5 |

Table 15. Crashing Costs

Normal Total Cost : 1190 per day = 1190*7=8330 per week

Choosen activities for reduction : A,B,C,D,E,G,H

New Cost : 1190+5+5+5+5+5+5+5=1225 per day = 8575 per week

So with additional 35 per day we can recover from a crash of 1 week. (35*7=245 per week)

# 3. REQUIREMENTS ANALYSIS

This online medicine shopping system is designed for the use of 4 actors :

- Patient

- Doctor

- Pharmacy Companies

- Admin

- Admin: The system admin can be thought as the manager of the system. He/She will be able to do all of the functionalities that other users can (indicated below) , but it will be not restricted by that, he/she will also be able to handle system reports and manage user operations.

- Doctor : The doctor is like the medical advisor of the system. Just like any user he/she must first sign-up and then log-in to the system. Any patient who have a problem or concerns about their health issues will be able to contact the doctor and describe their symptoms. The doctor will be able to see patient history, make drug orders, return back an order, write e-verified prescription for the extension of already proven drugs, view drug information, order drugs, track drug order state, make preferred type of payment, contact pharmacy companies, will have access to chat rooms, report system errors and display working pharmacies in the region. The system also provides a function which orders the patient in emergency scale so that the most critic patient in a given day gets service from the doctor first.

- Pharmacy Companies : The pharmacy companies plays a huge role in the system since they are the ones providing all the drug orders. They will be able to see all drug orders and the drug stores will be automatically updated by the system when a new drug order arrives. They will be  able to track the drug statement that they sent, accepts return backs, accept online prescriptions, contact doctor and patient and report system errors.

- Patient : The patient can be thought as a customer for the system. He/she must first open an account and then log-in to the system. After logging in the patient will be able to view drug information, order un-prescribed drugs like vitamins, ask for medical advise from doctors, contact pharmacy companies about the production or delivery of a certain product, report side-effects of a drug to the doctor, track the current situation of the ordered drug, return a drug order, display the duty pharmacies in the region, get online prescription for the already accepted drugs from the doctors, report system errors and make preferred type of payment.

Important Note: Since it is illegal to write a prescription to a patient without observing him/her in the clinic face to face, the e-verified prescription in this report is only used for the purpose of extending the already verified prescripted long-term drugs.

## 3.1 Functional Requirements

## PATIENT FEATURES

### Description and Priority

The patient can be thought as a customer for the system. He/she must first open an account and then log-in to the system. After logging in, the patient will be provided a menu where they can select functionalities that they are allowed to use.

### Stimulus/Response Sequences

When a patient makes a drug order the order details are automatically saved to the system database and updated through out the whole delivery process to provide the user real-time tracking of his/her order.

When a patient requests to conduct a doctor, the system puts the patient in an emergency scale (0[just control]-10[life-threathing]) and provide service in this order to preserve system quality.

When the patient enters his/her currently used drugs the system automatically starts a timer for the end date of the drug and when timer runs out, the setted alarm will inform the user.

### Functional Requirements

- Patient should be able to track the state/location his/her order.

- Patient should be able to see his/her drug history.

- Patient  should be able to contact the doctor in case of any emergency or unexpected situation.

- Patient should be put in an emergency order when the system serves for their requests.

- Patient should be able to see the start and end date of special prescribed drugs and get a reminder when deadline is close.

- Patient  should be able to select the payment option.

- Patient should be able to conduct the pharmacy company directly.

- System should display all duty pharmacies to the Patient available in their region.

- Patient should be able to conduct system admin incase of an errored situtation.

## DOCTOR FEATURES

### Description and Priority

The doctor is like the medical advisor of the system. Just like any user he/she must first sign-up and then log-in to the system. After logging in the doctor will be able to provide the following functionalities in Section 4.2.3

### Stimulus/Response Sequences

When a doctor’s patient updates his/her drug information, the system will inform the doctor by sending a notification.

### Functional Requirements

- Doctor should be able to see all drugs that his/her patients used.

- Doctor should be able to advice a pharmacy to his/her patients in the web site.

- Doctor should be able to advice vitamins or supplements to his/her patients (no need for recipe).

- Each doctor should have a unique e-signature.

- Doctor should write online prescription with unique e-signature so that his/her patients order their drugs.

- Doctors should have their own pages so that their patients can contact them easily. (like subscription)

- Each Doctor should have chat rooms so that patients can send them their test results.

- Doctors should be able to request a specific drug from pharmacy companies to add their stock.

- Each doctor should provide their diploma or a file from their hospital in order to be registered as a doctor.

- Each doctor should provide his/her expertise so that he/she will not be able to write recipe which is not related with his/her area.

## PHARMACY COMPANIES FEATURES

### Description and priority

The pharmacy companies plays a huge role in the system since they are the ones providing all the drug orders. The functionalities provided for the use of pharmacy companies are listed below in Section 4.3.3

### Stimulus/ Response Sequence

Once a user makes an order request, the order request database will be updated and the pharmacy company will be informed about the new drug order.

If the ordered drug is somehow not able to be delivered, then the pharmacy company will send an alternative/equivalent drug list and return back the money of the previous order.

Once a user makes a payment, this system will transfer the money from the user account to the pharmacy company bank account.

If a pharmacy company posts a new drug advertisement on their page, then the users of the system will be notified about this new update.

### Functional Requirements

- Pharmacy companies should be able to see website drug orders/requests to prepare their drug stores.

- Pharmacy companies should be able to post new released drug advertisement on the main page if and if the drug is OTC.

- Pharmacy companies should be able to contact the website customer if the drug they ordered is not produced anymore or give information about on equivalent drug.

- Pharmacy companies should be able to retrieve customer comment/feedback thruogh the website about the drugs inorder to be used in the research and development of drugs.

- Pharmacy companies should be able to enroll to the website by providing necessary information. If accepted by admin, they should be added to the system and log in, log out using this system.

- Pharmacy companies should be able to recieve their money through the system, once the customer purchases the drug. ( Customer bank account -> Company bank account)

- Pharmacy companies should be able to inform customer about shipping status of the drug. ( Teslim edildi/ Onay bekliyor/Yolda)

- Pharmacy companies should be able to update their own page with their own products ( Upload/Modify/Delete)

- Pharmacy companies should be able to send online verified receipt to the customer and accept return backs for a period of time ( ex=4 days)

- Pharmacy companies should be able to report illegal circumstances to the website admin.

- Pharmacy companies should be able to contact the doctor in order to send their drug samples when a new drug is produced.

## ADMIN FEATURES

### Description and Priority

The system admin can be thought as the manager of the system. He/She will be able to do all of the above functionalities of other users , but it will be not restricted by that, he/she will also do the additional functionalities listed below in Section 4.4.3.

### Stimulus/ Response Sequence

The user of the system will click the report errors section and enter the error in order to be read by the system admin.

### Functional Requirement

- The system admin must be able to manage all system users.

- The system admin should be able to manage e-mail server settings.

- The system admin should be able to manage seo settings.

- The system admin should be able to edit the required customer fields during the registration time.

- The system admin must be able to backup all the files and databases.

- The system admin must be able to change the VAT rate.

- The system admin must be able to activate the maintenance mode.

- The system admin must be able to force the customers to order something with user registration.

- The system admin should be able to see and answer all support tickets.

- The system admin must be able to add and modify currency.

- The system admin should be able to change company information.

- The system admin must be able to exchange the default language of the website..

- The system admin must be able to see all user log records....

- The system admin must be able to change the template of the website.

## FEATURES AVAILABLE TO ALL USERS

### Track Order Details

#### Description and Priority

Once a user logs in  and makes an order, the system will save all the order details in the system database for future tracking and information obtaining purposes. The system will show the order ID, current situation of the order (delivered, waiting for confirmation, on road, etc. ) and whether the order is completed successfully or not. This is a high priority feature in terms of providing trust to the end user and the ability to track the correctness of operations.

#### Stimulus/ Response Sequence

Once a user makes an order, the view orders page will be updated by appending this new order to the end of the previously available orders. The user can click on this link to observe the details of his/her order.

#### Functional Requirement

- The list should order details, content and delivery status.

- The list should be updated in real time simultaneously with the changes in order status.

- Any error/exception on the order(ex: unable to deliver) will be reported and money will be returned back.

### Search For Particular Drug

#### Description and Priority

This feature is implemented for the use of patients and doctors who wants to order or get informed about a drug. This is a high priority feature since it implements a core functionality in our system.

#### Stimulus/ Response Sequence

### After logging in, the user will go to the search button located at the top of the main page and type the drug name which they want to find out about. The system will search the databases and find the related drug information and display it on the screen. It will also provide options like making a drug order for the requested drug. If a drug can not be found, the system will display an error message. If the drug is available but not in enough amounts, the system will again show an error message.

#### Functional Requirement

- Users should be able search the drugs by typing their names in the search button.

- In case of an error ( like not available), the system should be able to provide an appropriate warning message describing the error and the solution.

### Create Account (Signup)

#### Description and Priority

### This function is designed for users who visit the page for the first time and plan on  using the website for drug ordering or consulting purposes. By creating an account, the users can save their purchasing details, illness histories, previous diagnostics and many more for future usage and simpler access. This is a high priority functionality since nearly all other functionalities depend on this functionality and should be implemented before performing any other operation. This is a high priority operation since it is the first operation to be performed by every user.

#### Stimulus/ Response Sequence

### Once you type the website link on your browser, the page will direct you to the homepage. In the homepage, users who wants to create an account will click on create account option and fill the necessary blank spaces with their information on the presented form. Once an account is successfully created, the users must log-in to the webpage to continue with their operations.

#### Functional Requirement

- The system should be able to allow users to enroll to the webpage once necessary informations are provided.

- If an invalid input is typed for any blank space in the create account form then the system will send a warning message indicating the source of the error and correction methods that can be taken.

### Update/Modify User Information

#### Description and Priority

### This function is designed for users who already have an account created in the system. If they want to add a new information or if they want to change a previously available information about them on the website, they must first provide a valid documentation proving the correctness of the information and once accepted by the admin, the user modifications will be made. This is a high priority operation since the inaccuracy in any of the fields in the user information form will result in accurate advises from website doctors and companies. That is also why the system requests for certified changes.

#### Stimulus/ Response Sequence

When a user logs-in and enters his/her personal page, they should click Modify Information Button and modify the related information. Once this operation is performed a notification will be sent to the system admin. If the system admin accepts the changes the system will be modified, else the system will remain in the initial state.

#### Functional Requirement

- The system should provide users the option to modify the information.

- The system should check if the information is valid/confirmed from a higher level of organization.

- The system should return to the initial state if the information they presented is not valid.

### Make Payment

#### Description and Priority

The users who orders a drug must pay the price to the pharmacy company. For this purpose the system provides 2 options : 1. Pay At Door 2. Pay Online . The first option is especially for the use of older people who won’ be able to perform online payment operations. In this case the drug will be first delivered and cash will be obtained once the drug comes to the location. The system will be updated and show that the price is paid. In the second option the system will display a form where you enter your card details and if they are valid money is automatically transferred to the pharmacy company account. Again the system will be updated and show that the price is paid. This is a high priority operation since money transactions must be  made carefully.

#### Stimulus/ Response Sequence

Once an order is made, the system will move on with the make payment state and perform the described operations.

#### Functional Requirement

- The users should be able to decide on whether to pay at door or pay online.

- The system should automatically update the order status from unpaid to paid once money transfer is made.

### View User History

#### Description and Priority

As described, any one who enrolls to the system will have an independent page where they put their personal information like name, surname, date of birth, country, previous illnesses, current illnesses, drug history, etc. Any patient who would like to recheck or any doctor who would like to know more about their patients or any pharmacy company who would like to make a more relatable drug advertisement to a patient will be able to view the patient history. This feature is available for the use between patient-doctor, patient-pharmacy company and doctor-pharmacy company. Not patient-patient in order to preserve patient rights. This is high priority feature since nearly the accuracy of all operations depend on the information presented in this section.

#### Stimulus/ Response Sequence

Once an user is logged in , he/she will be able to see their history in the in About Me Section of their personal pages.

#### Functional Requirement

- The users should be able to see their own history.

- The patients should not be able to see other patients history.

- The doctors, pharmacists and patients should be able to see each others history.

### Make Order Request

#### Description and Priority

If a user searches for a drug and decides on purchasing the drug, he/she must make an order request. This is a high priority feature since it is a core functionality in our website.

#### Stimulus/ Response Sequence

The order will be made by clicking the make order button after searching for a particular drug. The system will ask for amount and purpose of use details. It will not ask any personal details since they will be available in the users history in their accounts already. Once successfully completed, the system will move on with make payment step.

#### Functional Requirement

- The users should be able to make drug orders for the drugs available  in the system.

- If a drug is not deliverable the system will warn the user showing a appropriate message on the error source and options on fixing the problem.

- Once an order is made order request must be automatically updated so that the pharmacy companies will be informed about the new orders. Once a new order is added to the database, a notification should be sent to the pharmacy companies.

### Show Working Pharmacies In The Region

#### Description and Priority

If somehow the system is not available to operate or the serving list is too long such that there are a lot of delays, the system will check your region and display all duty pharmacies with their working hours so that you can get a help in the closest local health center in case of an emergency. This is low priority feature since it does not require any website related operation.

#### Stimulus/ Response Sequence

If the user is logged in, the user will be able to click on the Display Pharmacies and see the pharmacies in his/her region.

#### Functional Requirement

- The system should be able to check the region where the user leaves from user information and display all duty pharmacies with their working hours and locations.

### Report Errors To System Admin

#### Description and Priority

Any user observing any problem related with technical issues of the website must be able to inform the admin for corrections.

#### Stimulus/ Response Sequence

The logged in users should send a message to the system admin, describing their problems by clicking the report errors button on the bottom of the page.

#### Functional Requirement

- The users should be able to decide on whether to pay at door or pay online.

- The system should automatically update the order status from unpaid to paid once money transfer is made.

### Log-in Operation

#### Description and Priority

Once the user creates an account, they should be able to log-in to the webpage by entering their username and passwords. This is a high priority process since it is the beginning of everything.

#### Stimulus/ Response Sequence

Log-in section is in the homepage of the website. When the user enters the username and password, the system will check if  there exists a correct matching in the system database. If there is , It will prompt the user to their own page, else it will ask the user to re-enter the things again.

#### Functional Requirement

- The user should be able to log-in to the system when the username and password is entered correctly and the account is already created.

- If there is no match or an error, the system will ask for a re-enter operation.

### Log-out Operation

#### Description and Priority

The user should be able to securely log-out from the webpage by simply clicking the log-out button. This is a high priority process since it may lead to security issues.

#### Stimulus/ Response Sequence

The user when done with the website will click on log-out button and the system will return to the homepage.

#### Functional Requirement

- The users should be securely log-out from the website.

## Non-Functional Requirements

## Performance Requirements

Performance requirements of our web application defines how well the e-Commerce for Online Medicine Shopping system performs certain functions which were gathered and analysed by the end users, under specific conditions. You will be able to find information related with speed of response, throughput, execution time and storage capacity. The service levels comprising performance requirements are often based on supporting end-user tasks. We have to mention again that speed of the application also depends on the user’s internet speed.

- The website should be able to serve 100,000 people without problems at the same time.

- The response time of the system should not exceed 2 seconds.

- The user who does not perform more than 5 minutes should automatically disconnect from the system.

## Safety Requirements

The safety requirements defines what will be our approach for the purpose of  risk reduction in our system.

- The system should allow up to 100,000 people to use the number of entries simultaneously to prevent freezes / delays.

- The system should work 24 hours a day, 7 days a week.

- The system should keep the information and stock status of all medicines in pharmacies up to date.

## Security Requirements

This section of our report indicates our approach that enforces security. It can be directly tested and observed. Here we will give attributes that are related with access control, data integrity, authentication, and wrong password lockouts.

- The system should also record all past transactions.

- System security must meet HIPAA requirements.

- For invalid and malfunctioned operation the system will restart in order to prevent data loose as well as safe operation within 5 seconds.

- Only admin can view and change all information in E-Commerce For Online Medicine Shopping System.

- The system should keep its backup daily.

## Software Quality Attributes

This section of our report will lists the areas that need to be reviewed and audited in order to be claim that our product is high quality.

- The system must have a modular and readable code structure in order to change unwanted locations or integrate additional features easily.

- In order for the system to work without problems in different operating systems, a compatible code language should be preferred for each system.

- In order for the errors occurring in the system to be more easily understood and resolved faster, the detailed report of the process that the problem occurred has to be conveyed to the admin.

- The system needs to distinguish between the patient entrance and the pharmacy entrance and arrange the authorities accordingly.

- Every unsuccessful attempt by a user to access an item of data shall be recorded on an audit trail.

# Other Requirements

Usability

- The error rate of users submitting their payment details at the checkout page mustn’t exceed 10 percent.

- There should be no information in the system that does not concern the user, and the drug information provided should be understandable.

Scalability

- In order for everyone to use the system comfortably, each user must serve at 500 kbps bandwidth.

- A backup server should be kept in order to prevent the users from being victimized in the possible server crashes of the system and processes should be continued on the backup server until the problem is fixed.

## 3.3 Realistic constraints

Although this product is a well-designed product intended for the long term usage, there exists some realistic constraints when it is presented to the real world :

- Not everybody can use the system. Companies who decide to use this system will require to make a specific amount of investment both software and hardware point of view in order to broden their coverage areas.

- Since the product is mainly software based, it will not cause any additional environmental problem. But the implementation of the system ( the production of drugs, transportation etc) will continue in the traditional way and hence may continue causing environmental problems if it already causing initially.

- People below age 18 can not use the system. If it is required for them to use it, it should be advised by an adult above age 18.

- People having no previous prescription written face to face by a doctor, will not have the chance to purchase prescribed drugs due to ethical issues.

- Every operation will be under control of health government.

- Unconscious consumption of unprescribed drugs (such as vitamins and minerals) may put individuals health in danger.

- There may be out of stock moments where there is a large demand on a product leading to “unavailable drug” situation.

## 3.4 Ethical issues

People with bad intentions may use this product in an unintended and criminal way. The following ethical issues must be taken into account when anybody uses this web application :

- Medical websites, more than any other type of site on the Internet, should ensure visitors' personal privacy and prevent personal medical information, including patterns of use and interests, from being sold, purchased, or inadvertently entering the hands of marketers, employers, and insurers.

- With telemedicine, many states already require licensure in their state before an out-of-state physician can electronically provide services to patients

- Researchers are not allowed to gather information for research projects under the guise of "naturalistic observations" from chatrooms without participants being aware they are part of a study and merely participating in public forums does not  imply informed consent.

- Determining which parts of the traditional research methods can be adopted or adapted for use on the Internet and which will need to be discarded as non-adaptable.

- Some diseases may affect the human behavior and identity (such as schizophrenia ) and the use of online medical services may materialize these concerns

- Individuals who give wrong information about the disease and try to fool the system take their own risk of their safety and health.

- Managing health conditions at home or at residential care may contribute to self-isolation of users.

- The online medical services can limit assessment of a patient’s condition to a narrow range of easily measurable or quantifiable considerations, which could bias assessment towards an overly optimistic prediction of the technology’s effects.

# 4. DESIGN

## 4.1 High level design (architectural)

Here in the given system architecture diagram you can see all system components and all external systems as well as their interactions and interfaces.

Figure 4 : System Architecture Diagram

The explanation of the main components are presented here :

- Mail Server – A mail server (or email server) is a computer system that sends and receives email. In many cases, web servers and mail servers are combined in a single machine. However, large ISPs and public email services (such as Gmail and Hotmail) may use dedicated hardware for sending and receiving email. Mail servers send and receive email using standard email protocols. For example, the SMTP protocol sends messages and handles outgoing mail requests. The IMAP and POP3 protocols receive messages and are used to process incoming mail.

- MySQL Database - MySQL is the world's most popular open source database. With its proven performance, reliability and ease-of-use, MySQL has become the leading database choice for web-based applications, used by high profile web properties including Facebook, Twitter, YouTube, Yahoo! and many more. It is used to store and access to all data.

- Web Server – A web server is server software, or hardware dedicated to running this software, that can satisfy client requests on the World Wide Web. A web server can, in general, contain one or more websites. A web server processes incoming network requests over HTTP and several other related protocols. Web pages delivered are most frequently HTML documents, which may include images, style sheets and scripts in addition to the text content.

- Ordering System – It is a subsystem that is used to order one or more products in the system and also includes the payment system itself.

- Language System – It is a subsystem where users can change the languages of web pages according to the languages supported by the system.

- Category System – It is a subsystem that is made to categorize the products available in the current system.

## 4.2 Software design

In this section we will explain our system using UML Tools and Diagrams to give our development team and the end customers who understand and have a knowledge about software engineering terminology a deeper presentation.

CONTEXT DIAGRAM

Fig.5 : Context Diagram

Here in the above context diagram you can see the main system which is the “e-commerce for medicine shopping” in the middle indicated by  the label “0”. Around the main system you can see the actors and other systems interacting with our system. You can see what functionalities are expected from these systems on top of the arrows. The direction of the arrows indicate whether the functionality is coming from the external system to our system or vise versa.

To give a simple example the patient will be able to conduct the following functionalities using the system :

- track the state/location his/her order.

- see his/her drug history.

- contact the doctor in case of any emergency or unexpected situation.

- select the payment option.

- conduct the pharmacy company directly.

- conduct system admin incase of an errored situtation.

And in return the system should provide the functionalities below to the patient :

- put in an emergency order when the system serves for their requests.

- see the start and end date of special prescribed drugs and get a reminder when deadline is close.

- should display all duty pharmacies to the customer available in their region.

This simple principle applies to all other external actors and systems shown in the diagram and serves the purpose of showing system contents very clearly. As a rule of context diagram we didn’t show any databases.

LEVEL 0 DATA FLOW DIAGRAM

Fig 6. Level-0 DFD Diagram

The data flow diagram above shows level-0 processes and the way in which data comes and goes from these processes. Additional to the context diagram the data is shown as parameters just like functions and databases are also implemented. Here we have 13 processes. These are the main processes in our system shown very briefly and in a very general form. These systems divide further into several subsystems giving more and more details about the data flow among the processes. To implement those details we need to draw level1 DFD ,level2 DFD , and many more. Here we only draw Level0 DFD as indicated in the Homework description. Since this system have many functionalities, there are many data coming and going to the processes. To give an example:

We can take a look at the 5.0 Give Drug Order Process :

This process is dealing with the actors Patient and Doctor.

Once a patient decides to make a drug order, he/she sends the PatientID, Drug Name and Drug Amount to the system. The system then puts this order into Drug Order Request Database using the parameters DrugID, DrugName, DrugAmount, Estimated Delivery Time, Placement Of The Drug  so that pharmacy companies can access and receive the drug orders. Pharmacy Companies have also access to this database and can modify it by reducing the amount when a drug delivery is completed. After putting the order in the database, the system then returns the OrderID to the patient so that he/she can use it for tracking the drug order or receving the purchased drug. 5.0 Give Drug order process also have subprocesses for tracking the ordered drug which will be shown in more details in other levels of DFD diagram. That is why you can see the system returns DrugID, DrugName, DrugAmount, Estimated Delivery Time, Placement Of The Drug to the patient. By this way the patient can easily observe the current situation of his/her order.

Similary the Doctor can also use this process. Once a Doctor makes a drug order (either for himself/herself), he/she will put the DoctorID, Drug Name and Drug Amount to the system. The system find the requested drug and put it in the order request database using the datas arrived : DrugID, DrugName, DrugAmount, Estimated Delivery Time, Placement Of The Drug for the purpose of informing the pharmacy companies. The system have subsystems which searches for the drug using the drug name and checking whether the requested drug amount is available in the pharmacy company. But again these processes are not shown since they are subprocesses and will be shown in more details in further Levels of DFDs. After system puts Doctor’s order in to the database, it will return  DrugID, DrugName, DrugAmount, Estimated Delivery Time, Placement Of The Drug so that the Doctor will be able to trace his/her order anytime they like. These information will be used for receving the drug as well.

This dataflow structure works for all other actors,external systems and processes providing what kind of data is expected from which systems, what kind of data comes out from which system and  how the system handles data arrivals and returns.

Level-1 DFD For Process 7.0 Make Payment For Patient

Fig.7 : Level 1 DFD 1

Here in this Level-1 DFD diagram we went into 1 step more detail about make payment process for the user patient. If you take at a look at the original Level-0 diagram you can see that the number inputs coming to this process as well as the parameters and the number of outputs going out of this process as well as the parameters are exactly same as the Level-1 diagram since it is a rule that has to be satisfied. When a patient tries to make a payment, the system will display 2 options; he/she either decides to pay for  the order online by card, or pay at door by cash. Once an option is selected the user will be directed to the appropriate option and finally finish the operation by accepting a receipt about operation details.

Level-2 DFD for 7.0 Make Payment Process For Patient

Fig8 : Level-2 DFD1

Here in this Level2 DFD for the same process it is divided into even more detailed processes. Again the incoming and outgoing number of inputs and outputs and their contents are the same satisfying the diagram rules. Here you can see that the processes in Level-1 diagram are displayed in more details. Display options process now gives the choice of displaying the options based on the selected criteria : based on most popular payment methods or based on your last payment method. The option selected here will be come to 2 different options : Pay by card or Pay by cash. But here as you can see these processes also divided into further details. Now for pay by card, the user can select by which banking company he/she wants to operate on. For Pay by cash the user can select either to pay at door using the local money unit that is currently used in their countries or he/she can select the globally accepted cash type in our system. All these information will be sent to the 7.3 process which is receive Receipt by check-out information when transaction section is done. 7.3 is also divided into more details by showing 2 options : Get an online e-verified receipt that is obtained between the system and the contracted banking company or get a direct hard-copy receipt. These divided processes can also be divided into further more details in other higher levels of DFDs.

Level 1 DFD For 11.0 Manage System Reports And Features Process For Admin

Fig 9 : Level 1 DFD2

Here in this Level-1 DFD you can see how the manage reports and features system is operating in 1 step more details. This process is divided into 2 sub processes which handle the operation in 2 ways : system level which generally deals with system performance issues as well as quality aspects and user level which defines user based operations. They all send operation information showing whether operation succeed or failed. In the below Level-2 DFD diagram for the same process you can see even more details.

Level-2 DFD For 11.0 Manage System Reports And Features Process For Admin

Fig 10 : level-2 DFD2

In the above Level-2 DFD diagram you can see the processes even in more details. Process 11.1 in Level 1 diagram now have 2 sub processes indicating whether the user level operation should be about user errors or user requests. Process 11.2 is now indicating whether the admin should perform the system level operations shown with labels from 11.2.1 to 11.2.9 . The diagram can be divided into further details in higher levels of DFDs. Each process then send the operation results whether it succeed or failed. Finally these results are displayed to the system admin.

USE CASE DIAGRAM

Fig 11 : Use-Case Diagram

Here in this use-case diagram, you can see the actors and external systems interacting with the main processes in our system. The main processes here have 2 different additions : <includes> and <extends>.

<includes> keyword is used to indicate that the process in which the arrow is coming out from includes the process which is showed by the end of the arrow. So whenever the root process the applied, we know that before this process, the <includes> process is also applied. For example : “Make Payment” Process in our system is used for conducting any kind of payment operations when a drug order is made. Just like in other systems available in the market, in order to make a payment you need to first sign-in in to your account in order to get your personal account information. No system will accept anonymous payments. That is why before every Make Payment Process you have to implement Log-in/Logout Process. Actually if the user (doctor/patient/pharmacy Company) have an account, regardless of his/her operation with the system, must first sign-in to the system. That is why nearly all processes in our system includes the Log-in/Log-out Process. Only Create Account Process does not include anything. That is because Create Account process is used by individuals who have no previous interaction with the “e-commerce for medicine shopping” system. Once an account is created, the user will now use the log-in/logout process whenever he/she wants to conduct an operation.

On the other hand, some processes use the <extends> keyword which can be easily seen in the use-case diagram. The <extends> keyword is used to indicate that the user at that point have a choice or option to continue in the way they wanted. Again if we take a look at “Make Payment” Process, it has 4 branches that used the <extends> keyword. These branches are : Pay Online, Pay At Door, Send Receipt, Order Receipt. Once a user chooses to perform make payment action which holds all money related operations inside, he/she will have a choice to select one of the 4 branches to continue. If he/she selects to pay online, the other 3 will be considered as not existing and the user will continue operating on this branch and make the payment by card. If he/she decides to make the payment by cash, he/she will select Pay At Door Operation and the system will forward the user to the related operations placed on that branch. If the user makes the payment but wants to receive a receipt then he/she will order the receipt and the banking company will direct the receipt to the indicated user. If user is the banking company then he/she will have an optional selection that is send receipt where they send the receipt to the order owner. The 4th branch is online available to the banking companies.

This idea applies to all actors,external systems and process shown in our use-case diagram.

SEQUENCE DIAGRAMS (ONLY THE IMPORTANT ONES)

- FOR PHARMACY COMPANIES:

“Pharmacy companies are able to see website drug orders/requests to prepare their drug stores and update/modify the requests when a delivery is completed or the drug amount currently available is not enough. “

User: Patient (Same applies when it is a doctor) , Assumption : The Patient already have an account so he/she only logs-in, does not have to create a new account.

Fig.12 : Sequence Diagram For Pharmacy Companies 1

In this sequence diagram, the patient first log-in to system using his/her username and password. The system displays the main menu page to the user. The user using the search button searches for the requested drug. The system among all the available drugs, finds the drug that matches with the search information and returns the related drug details. The user then decides on making a drug order and presses give drug order option indicating the drug amount that they want. The system searches if the requested drug amount is currently available in the system. If It is available without sending any warning message, the system will ask for card details. If the entered card details are valid , then the system will display the drug price and ask for confirmation to the user to decide if the purchasing operation should be conducted or not. Once the confirmation is received, the money from the customer account is delivered to the bank account and related receipt arrives to the system. Once receipt arrives the system then places the drug order to the order database so that pharmacy companies are informed about this new order. The orderID, Estimated Delivery Time and Drug Status is send back for tracking purposes and combined with the receipt and displayed to the user. The pharmacy companies who receives and operates on the order using the drugID and drug amount have the ability to modify the database so that the status of the drug is changed from ordered to delivered. Once it is changed the order request database, the information will be displayed to the user and the user will be informed about the new status of his/her order.

In this sequence diagram you can also see the alternative cases where the requested drug is not available/found in the system, the requested drug is found but the requested amount from the user is more than the available amount therefore unable to proceed operation, the card details are invalid or the money transaction is not confirmed. When these cases occur the necessary action to be taken is represented in the diagram.

- FOR PHARMACY COMPANIES:

“Pharmacy companies should be able to contact the website customer if the drug they ordered is not produced anymore or give information about on equivalent drug.”

Assumption : Patient already logged in to the system and completed the give drug order process successfully.

Fig 13:Sequence Digram for  Pharmacy Companies 2

In this sequence diagram the patient initially logs in and makes a drug order. After making a drug order somehow ( ex: a new government rule comes that the drug will have a lot of side effects and the production must be stopped) after receiving the drug order, the  pharmacy companies says that the drug is not produced anymore. Once the company informs about this situation the paid money will be returned back and the customer will be given the chance to ask if there is an equivalent drug ( in some serious cases drug most be taken regularly, so pharmacy companies should be able to advise an equivalent drug). Once the customer decides to ask for equivalent drugs, this request will be delivered to the pharmacy company just like a regular order. This order will be treated differently and the pharmacy company will sent a list of drugs that can be used in absence of another drug. The user from this list of drugs will select the drug and make a new give order operation. He/She will now pay for the new order, so he/she will enter the card details. Once it is confirmed that the card details are valid and operatable, this system take the money from customer account to the bank account. Since the purchasing operation is completed, the customer order will be placed in Order Request Database so that the pharmacy company will be able to access, see and deliver the new product. Once pharmacy company sees the new drug order and performs necessary operations, will update the order request database and send NewOrderID, EstimatedDeliveryTime and Drug Status(ordered->delivered) to the customer. Now the customer has full details on the new drug order he/she made.

In this sequence diagram you can also see the alternative cases where the alternative or the equivalent drug is not available therefore can not substitute a drug instead of another ( when there is an available alternative drug, before advising it to the user, the drug company checks whether there is enough sources therefore there is no need to add an alternative sequence for that case) or the card details are invalid. When these cases occur the necessary action to be taken is represented in the diagram.

- FOR DOCTOR :

“Doctors should be able to request a specific drug from pharmacy companies to add their stock.”

Fig 14:Sequence Digram for  Doctor1

In the above sequence diagram it is shown that a doctor (who already has an account for E-Commerce for Online Medicine Shopping) tries to buy a specific drug, if he/she can’t find that drug in any of the pharmacy companies in the web site he/she will make a request for it.

In the beginning user enters his/her password and e-mail to login the web site. System checks weather both password and e-mail are correct from the user database. If wrong user will re-enter his/her password and e-mail, if not he/she successfully enters to the web site and system will display main menu. After that, all he/she will do is to write the name of the desired drug in the search bar. After that, system will check if the desired drug is available in any of the pharmacy companies by checking products database. If the drug is not available, the system will send the user a warning message that the drug is not available and it will ask the user if he/she want to make a request for it. If the user wants to make a request, the system will send a message to Pharmacy Company. If the drug is available, the user will choose a company where he/she wants to buy the drug. After that, user will enter his/her card information and after validation money will transfer to the bank and system will send a message to the pharmacy company that the payment is done so that they can send the drug to the shipping.

- FOR DOCTOR :

“ Doctors should be able to request a specific drug from pharmacy companies to add their stock.”

Fig 15:Sequence Digram for  Doctor2

In the above sequence diagram it is shown that a doctor (who already has an account for E-Commerce for Online Medicine Shopping) tries to display his/her patient’s past drug list. Each doctor has their own portal in the web site so that his/her patients can subscribe his/her portal. By this way, doctors can be able to view his/her patient’s medical information. In above sequence diagram user (doctor) has his/her own portal and he/she has several patients who subscribed to his/her portal.First of all, user already has an account so he/she can login to the web site. After that, system will display the main menu to the user. User will choose his/her patient from the patient list from doctor database, which is displayed by the system after user click to ‘my patients’ button in the menu. After choosing patient, system will display patient information from patient database so that user can see what drugs his/her patient have used so far or currently using. In addition to this, according to these information, user (doctor) can find a drug and/or a pharmacy company from the web site and share it with his/her patients. If the desired drug is not available in any of the companies, he/she can also request that drug from any pharmacy company as we mentioned above.

- FOR PATIENT

“Patient will be able to see the purchasing history.”

Fig 16:Sequence Digram for  Patient 1

In the sequence diagram above, it is shown that a patient who has previously opened an account for him can examine all the drugs he / she has previously used or purchased. The patient first enters the website designed for E-Commerce for Online Medicine Shopping. The site asks for account information in order to grant roles and authorizations of the user who wants to login. The user enters the account information (e-mail / ID number and password) and then the site sends it to the security-prepared database to determine if there is an account for this information and what type of user, if any. If an account for this information is not found, the security database reports this to the shopping system and sends the error message to the user in the shopping system and sends it to the login screen to try again. If the database verifies that the entered information is a patient account, the shopping system redirects the patient to the home page. The patient clicks the personal information section to view information about himself/ herself. The patient can obtain the information he / she wants by entering the drug information passed through these options.

- FOR PATIENT :

“ Patient makes drug order indicating prescription (prescription required drugs) ”.

Fig 17:Sequence Digram for  Patient2

The sequence diagram above shows a patient who marks his order according to his urgency and places the order. Assuming that the patient opened an account and entered successfully, he was directed directly to the home page  and then the patient enters the prescription code given by the doctor to the system. The main system searches the prescription code entered in the database and finds which drugs are written on the prescription. The system then delivers the list of drugs to the appropriate pharmacy to the patient. Assuming that the drugs exist in the pharmacy, the system is informed that the drugs are ready. The system displays the order to the patient and the patient creates the order with the urgency order (high-low). The system transmits the patient's information to the pharmacy and the pharmacy transmits this information to the order database, the order database confirms these orders and sends the confirmation message to the main system. The system passes to the payment section as a last step and requests the payment method from the user. The user chooses to pay by card and writes the card information. The system sent this information in the bank database and shows the general report to the patient.

- FOR ADMIN :

“Admins should be able to manage e-mail settings.”

Fig 18:Sequence Digram for  Admin1

As seen in the diagram above, you can see that admin users will already have an account at startup. There will be some inputs we need to log in to the system.These are might be username-password or email-password binary. Firstly , user makes a request to the admin login page and then fills the required inputs to login the system. The system checks the user information using the database base records.If it is success ,the user is going to be authenticated and automatically redirected to the admin dashboard. Otherwise , the system will display a error message to the user.

Admin will make a request to open e-mail settings page. The system’s database is going to send a query to the system database to get the default e-mail server settings. On that page, user needs to input a test e-mail address to send a test mail. After that operation , firstly ,the system’s database is going to check whether the written mail server information is correct or not. If the validation is correct ,the system make a request the mail server. So ,the mail server sends a test mail to the written test e-mail address and the system shows a successful message to the user.Otherwise , it shows a connection error.

- FOR ADMIN :

“Admins should be able to manage users.”

Fig 19:Sequence Digram for  Admin2

As seen in the diagram above, you can see that admin users will already have an account at startup. There will be some inputs we need to log in to the system. These are might be username-password or email-password binary. Firstly , user makes a request to the admin login page and then fills the required inputs to login the system. The system checks the user information using the database base records. If it is success ,the user is going to be authenticated and automatically redirected to the admin dashboard. Otherwise , the system will display a error message to the user.

Admin is going to make a request to the add a new user page and type the required fields to create a new user. This process will be done by calling a createuser function. It sends a query to the database to create a new user and also checks for some necessary conditions. As seen in the diagram , there are two condition that must pass to create a user. If the given username is already exist and the e-mail address is already exist , the system demonstrate an error message based on the error made.

Business Process Modeling (BPMN)

Fig 20: Business Process Modeling

The BPMN Diagram above illustrates the e-commerce for online medicine shopping system’s  business processes in the form of a diagram similar to a flowchart, making it easy for technical and non-technical observers to understand the processes involved. Since we have 4 users there are 4 sections in the BPMN diagram. Each section describes how a specific user interacts with the system.

For example a patient will first enter the website and log-in just like other users do. Then he/she will either enter a prescription to search for a drug or choose to display his/her personal information.

In case of selecting to display patient history : The user will have 2 options. He/she will either display her medical report or his/her previously purchased drug history. Once the corresponding information is displayed that business process will end, so the user will be able to select log-out and exit the system.

In case of entering prescription: The user will be able to search for a particular drug. The system will check if the drug is in the stock or not. If the drug is available in the stock, the search will be validated and the user will be forwarded to ordering and payment processes which we have again 2 options : by card or by cash. If the drug is not presented in the stock, then the system will either recommend an equivalent drug or if there is no such equivalent drug the system will simply make a new request to the pharmacy company indicating that the production of that special drug is needed. If the user decides to purchase an equivalent drug, then it will be first forwarded to the related doctor to get his/her advise and then if confirmed will be treated as a new drug order. Then that process will also finalise and the user will log-out.

Similarly doctor will be able to create a new drug order, view patient history just like patients but addition to that the doctor will be able to write e-prescription for the already approved drugs (face to face as a governmental rule).He/She will enter drug and patient information and validate the report by using his/her unique e-signature.

On the other hand, the admin which has the highest priority in our system, will be able to conduct all the mentioned processes above but addition to that, he will manage system reports and operate messaging issues. When managing the system reports he/she will conduct the routine checks and fix problems available in the system.

ENTITIY RELATION (E-R) DİAGRAM

Fig 21:E-R Diagram

The Entity Relationship diagram above illustrates the information models used in our system. Each entity can be taught as an object that belong to the system that describes the attributes or characteristics that are owned by themselves. Each arrow describes the kind of relationship or interaction between these objects. To give a simple example lets consider Patient and Order entities. The patients will have id , name , surname , email and password. The orders will have order id , item id , track id, customer id, order state, order date, shipping date, company id and total price. These attributes will give information about each object and hence describe and define how they will be treated in our system when serving for a functionality. The patients that are enrolled to our system will be able to give order to requested drugs. The orders will be given by users such as patients. Therefore you there exists a relationship between patient object and order object. The relationship name is receive, because the patient receives an order and the order is received by an patient. The relationship type is 1 to many. Because 1 patient can give many orders. If we consider the reverse order; many orders can be given by 1 patient. A similar relationship exists between doctor-order. Another example can be given between order and pharmacy company. The pharmacy companies have the attributes company id , name, email and password. Each pharmacy company produces a drug therefore they are the supplier of the order. Each order on the other hand will be supplied by a pharmacy company. Therefore there exists a supplies relationship between pharmacy companies and order objects. The relationship between them is 1 to many because an order can be supplied by many pharmacy companies ( because a order can be consisting of many different drugs) and many pharmacy companies can supply drugs to a certain drug.

LOGICAL DATA MODELING

Logical Data Modeling (LDM) :

We will create the below LDM from the above E-R diagram. We will consider the relationships and build the following relations based on the following rules:

- If relationship is 1-1 or 1-N add Primary Key of 1st to 2nd .

- If relationship is M-N, create a new table and add Primary Keys of both tables as Primary Keys.

Log_records(user_tag, user_type, time, description)

Patient(user_tag, patient_id,user_name, patient_name, patient_surname, patient_email, patient_password)

Patient_contact_info(patient_id, patient_phone, patient_address, patient_city, patient_country, patient_zip_code, patient_id)

Doctor(user_tag, doctor_id, doctor_name, doctor_surname, doctor_email, doctor_password, doctor_signature, doctor_experience)

Doctor_contact_info(doctor_id, doctor_phone, doctor_address, doctor_city, doctor_country, doctor_zip_code, user_tag)

Pharmacy_company(user_tag, company_id, company_name, company_email, company_password)

Pharmacy_contact_info(pharmacy_id, pharmacy_phone, pharmacy_address, pharmacy_city, pharmacy_country, pharmacy_id)

Category(category_id, category_name, status, category_site_title, category_meta_keywords, category_meta_description)

Products(category_id, product_id, company_id, category_id, production_date, consumption_date, stock_amount, price)

Products_info(product_id, product_name, product_id, product_type, product_img)

Order(doctor_id, product_id, company_id, order_id, item_id, customer_id, company_id, price, track_id, order_status, order_date, shipping_date)

As you can see the logical data models above are not in 3rd normal form. So if we put them in 3rd normal form and merge some of  the tables that we can combine , we will get the following

Log_records(user_tag, user_type, time, description)

Patient(user_tag, patient_id,user_name, patient_name, patient_surname, patient_email, patient_password, patient_phone, patient_address, patient_city, patient_country, patient_zip_code)

Doctor(user_tag, doctor_id, doctor_name, doctor_surname, doctor_email, doctor_password, doctor_signature, doctor_experience, doctor_phone, doctor_address, doctor_city, doctor_country, doctor_zip_code)

Pharmacy_company(user_tag, company_id, company_name, company_email, company_password, pharmacy_phone, pharmacy_address, pharmacy_city, pharmacy_country)

Category(category_id, category_name, status, category_site_title, category_meta_keywords, category_meta_description)

Products(category_id, product_id, company_id, category_id, production_date, consumption_date, stock_amount, price, product_name, product_type, product_img)

Order(doctor_id, product_id, company_id, order_id, item_id, customer_id, company_id, price, track_id, order_status, order_date, shipping_date)

In our system , we will implement the first logical model since it is way more efficient for performance and ease of data access.

Physical Database Tables :

Fig 22:Physical Database Tables

Here in the following physical database tables below, we indicated the actual database tables that we will use in our program. We show the Primary and foreign key attributes as well as their data types such as int and varchar().

ACTIVITY DIAGRAM

Fig23: Activity Diagram

In the above activity diagram , there are four users and two external hardware. These are admin, doctor, pharmacy company, patient, database and mail server. All have their own operations, process and activities. As an example, we showed the most important activities of each user. Initially, all users log into the system and these transactions are recorded to the logs table in the database.

- Admin can create a new user

- Admin can change the email server settings

- Admin can take a full backup of the sql and files.

Admin logs into the system and sends http requests to the add a new user page to add a new user. The information required for the new user is filled in and the validity of the entered values is checked. If applicable, user information is recorded in the database and a new user is created. If not, the fields that are wrong are displayed as an error message on the screen. admin can change the e-mail server information for e-mail sending. For checking this, for example, he can send a test mail by entering an e-mail address from the system. This activity sends a request to the mail server and when it is accepted, an e-mail is sent to the mail address and the successful message is displayed on the screen.

- The doctor can order a drug.

- The doctor can view patients' past drug orders.

We entered the system considering that the doctor has an account now. HTTP request is sent to the site for a new drug order from the page on the main screen. The doctor displays the products from this page and the product is sent to the cart after the product selection. Information such as credit card, etc. required for purchasing are entered and this information is checked for verification. if it is correct, the required fee is taken from the account, the product order is passed and the order information of the relevant product is sent to the user by e-mail and shows the order is successful message on the screen. If not, the required error messages are printed on the screen. The doctor displays the page of their users to see the products that customers have previously ordered and displays the order history from the tab here.

- Pharmacy company can manage its own product.

- Pharmacy company can show shipping status.

- Pharmacy company can manage its balance.

The pharmacy company is shown to have an account again and log in (Normally all user types have a registration page). The drug company sends an http request to access the relevant page through the main menu displayed to edit the products. From here, you can create a new product or change the general information of an existing product. When the product information is changed, the information is checked, if correct, this information is updated in the database and the successful message is displayed on the screen. If a new product is desired to be created, a http request is sent to this tab again and the required product information is filled. Such as product name, quantity, price , description etc. When verification is accepted, the product is created and a success message is displayed on the screen. The pharmacy company can change and display all of its own shipment operations according to the shipment status it will select. It displays all its own payments and balances on the home page. Required bank IBAN or account number is entered. If the information is correct, the requested amount is transferred to the bank account and reduced from the system balance. If the process is completed, the message successfully sent to the screen will be displayed.

- User can change its information

- User can purchase a product

- User can create a support ticket

We assume that the user, the patient, is already registered to the system. The user enters the password, user name or mail address information to log in to the system. This process performs a verification process and if the necessary information is correct, the user logs in to the system and this attempt is recorded in the log table in the database. If the user wants to change his / her own address or any information, access to the change my information page is provided. The user information to be changed is entered and saved. A verification process is performed again and the correct registration is made. If the customer wants to order a product, he displays the products and chooses the product he wants. The product is added to the cart and the payment page is selected. If the payment card is selected, the credit card is entered and the information is checked. If all the information is correct, the order is passed. Then the mail of the order information is sent to the user, the order is put on hold and the order successful message is printed on the screen. If users have any problems, it creates a support request. A department related to the subject is selected and the title and content of the support request are entered, and then the support request is created.

Related SQL Codes :

Create tabel Log_records (

user_tag int(20) primary key,

user_type varchar(100),

time varchar(100),

description varchar(100)

)

Create table Admin (

admin_id int(20) primary key,

admin_email varchar(100),

admin_password varchar(100),

admin_first_name varchar(100),

admin_last_name varchar(100),

template varchar(100),

language varchar(100),

created_at varchar(100),

updated_at varchar(100),

Foreign key admin_id references Log_records(user_tag)

)

Create table Patient (

patient_id int(20) primary key,

user_name varchar(100),

patient_name varchar(100),

patient_surname varchar(100),

patient_email varchar(100),

patient_password varchar(100),

Foreign key patient_id references Log_records(user_tag)

)

Create table Patient_contact_info (

patient_phone int(20) primary key,

user_address varchar(100),

patient_city varchar(100),

patient_country varchar(100),

patient_zip_code int(20),

patient_id int(20),

Foreign key patient_id references Patient(patient_id)

)

Create table Doctor (

doctor_id int(20) primary key,

doctor_name varchar(150),

doctor_surname varchar(150),

doctor_email varchar(150),

doctor_password varchar(150),

doctor_signature varchar(150),

Foreign key doctor_id references Log_records(user_tag)

)

Create table Patient_contact_info (

doctor_phone int(20) primary key,

doctor_address varchar(150),

doctor_city varchar(150),

doctor_country varchar(150),

doctor_zip_code int(20),

doctor_id int(20),

Foreign key doctor_id references Doctor(doctor_id)

)

Create table Pharmacy_company(

company_id int(20) primary_key,

company_name varchar(150),

company_email varchar(150),

company_password varchar(150),

Foreign key company_id references Log_records(user_tag)

)

Create table Pharmacy_company_info (

company_phone int(20) primary key,

company_address varchar(150),

company_city varchar(150),

company_country varchar(150),

company_id int(20),

Foreign key doctor_id references Doctor(doctor_id)

)

Create table Category (

category_id int(20) primary key,

category_name varchar(150),

status varchar(150),

category_site_title varchar(150),

category_meta_keywords varchar(150),

category_meta_description varchar(150)

)

Create table Products (

product_id int(20) primary key,

category_id int(20),

production_date varchar(150),

consumpiton_date varchar(150),

stock_amount int(150),

price int(1000),

company_name varchar(150),

Foreign key (category_id) references Category(category_id),

Foreign key (company_name) references Pharmacy_company(company_name)

)

Create table Products_info(

product_name varchar(150) primary key,

product_id int(20),

product_type varchar(150),

product_img varchar(150),

Foreign key (product_id) references Products(product_id)

)

Create table Order(

order_id int(20) primary key,

item_id int(20),

track_id int(20),

customer_id int(20),

order_status varchar(150),

order_date varchar(150),

company_id int(20),

total_price int(4000),

Foreign key (item_id) references Poducts (product_id),

Foreign key (customer_id) references Log_recors (user_tag),

Foreign key (company_id) references Pharmacy_company (company_id)

)

# 5. IMPLEMENTATION

5.1.  Tools, Technologies and platforms used

  - We will use HTML and CSS with JavaScript to make nice and dynamic user interface and making animations so that users can see system friendly.

  - We will connect database to the system by PHP and we will use MySQL as database.

  - We will not use external database for this project.

  - We will create enough amount of table in the database so that inserting, updating and selecting information from database will be much easier.

  - We will create tables in the database for each role (doctor, patient, Pharmacy Companies and admin) so that while updating role information this will make things easy for us.

  - We will avoid of using excess amount of code lines in order to increase the speed of the system and decrease the waiting time of the users.

FOR INSTALLATION DETAILS PLEASE CHECK THE kurulum.txt file in our project folder.

5.2 Algorithms and Coding Implementations

  - Standards

We used World Wide Web Consortium which is the international standard for the World Wide Web.

For security we used best encryption standards for database encryption in order to take user information safe.

# 6. TESTING

We would like to start this section by mentioning that it is not possible to guarantee that the tests performed will provide %100 coverage independent from the test numbers and contents. The statement  from Qurora “No software is bug-free but a tester brings Quality to a software. A good software testing company focus on quality bugs and aids in hurdle-free delivery.” would be a perfect fit in this case. It would be unrealistic and meaningless to claim that we have discovered all possible bugs available in a very large web application. However it is possible to increase the number of tests and observe that the number of discovered bugs will increase as well. That’s why we  performed repeated tests with the different Test Environments. Our time was not infinite, and within that limited time we wanted to conduct as many tests as possible. For this purpose we decided to choose our testing tools from online, open source and automated testing tools where we can include so much more test scenarios that we can use to test the website in a shorter amount of time. Once we were sure that every requirement in SRS Document is mapped to a functionality in our application and once every planned test, related with performance, security and other issues are completed and passed, we verified and validated our end product.

For testing stage we test two of our important requirements, which are very important for our system. We explained each of them individually (as two separate examples) below.

Test 1: In our first test we tried to create a user (patient type) to see a user can successfully create an account in our system. As you can see on figure 1.1 below, we entered necessary information to the registration form to create an account. If you look at the figure 1.2 you can see that the account is visible on admin panel which means the user account that we tried to create was successfully created.

Figure 1.1: Registration form.

Figure 1.2: User information section in admin panel.

Test 2: In test 2 we tried to create a ticket between a patient and a doctor where we can count this requirement as the most important requirement in the system as it provides communication between users (between a doctor and his/her patient in this case). On figure 2.1 below, you can see that the user (patient type) is trying to create a ticket by filling the ticket form. If the ticket will be created successfully, the message will be delivered to the doctor without any problem and as you can see on figure 2.2 below, the message of the user was delivered to the doctor successfully and doctor is able to view the message in his/her platform.

Figure 2.1: Creating ticket form.

Figure 2.2: The ticket platform of the doctor.

# 7. USER GUIDE OF THE SYSTEM

To begin with, in our system there are 4 types of users (Patient/Customer, Doctor, Pharmacy Company and Admin) where each one has different type of user interface in our system, so in this user guide we discuss the system for each user type individually.

Our system requires account to perform full functions. In diagram 1.a you can see a register page for a patient where it asks for several information which are going to be used in the system. After user entered his/her information in the forms all he/she need to do is pressing ‘REGISTER’ button at the left bottom of the page to create his/her account. If the user is not a patient and if he/she is a doctor or pharmacy company he/she should fill specific registration for those user types. So the user must select if he/she want to register as a doctor or a pharmacy company by clicking one of the ‘ARE YOU A DOCTOR?’ or ‘ARE YOU A PHARMACY COMPANY?’ buttons on the top right of the register form to open a new registration form.

Figure 1.a: Register page of patients.

If the user clicks ‘ARE YOU A PHARMACY COMPANY?’ button to register as a pharmacy company, a new registration form (figure 1.b below) will be opened. After this, the user must fill the from and then he/she should click ‘Create Now!’ button at the middle bottom of the form to create his/her account.

Figure 1.b: Register page of pharmacy companies.

If the user clicks ‘ARE YOU A DOCTOR?’ button to register as a doctor, a new registration form (figure 1.c below) will be opened. After this, the user must fill the from. In addition to these, users who want to register as a doctor should also upload a document which proofs that he/she is a real doctor. After doing all these, the user should click ‘Create Now!’ button at the middle bottom of the form to create his/her account.

Figure 1.c: Register page of doctor.

If the user already has an account he/she can simply login from the login page (figure 1.d below) which asks e-mail/username and the password of the user. After entering his/her e-mail/username and the password the user can login in by clicking the ‘LOGIN’ button at the bottom left of the login page if the entered e-mail/username and password is true, if not the user must try again. There is also a ‘Forgot your password?’ section in case that of forgetting password and also there is a ‘Remember Me’ check box so that users don’t have to enter their e-mail/username and password every time they want to enter the web site.

Figure 1.d: Login page of all users.

After this part we have categorised the user guide for each user type.

Patient:

As you can see in figure 2.a (below), after a patient login to the system that page will be displayed to the user. At the very top left of the page there is a language settings to change the language of the site and there is the money unit that the user can change while ordering medicines. There is also a search bar on the header part of the system to search necessary drug. The user can order the drug by clicking on it but the user should have an online receipt for the necessary drug in order to buy it. If there isn’t an error message will be displayed by the system (Figure 2.c). In addition to this, there are ‘CREATE NEW TICKET’ and ‘ACCOUNT INFORMATION’ where the patient can ask for an online recipe from his/her doctor (Figure 2.d below) and where user can change his/her information (Figure 2.e below). Also there is ‘ORDER’ and ‘TICKET’ section to track order and ticket status.

Figure 2.a: Home page of patient.

Figure 2.b: Order page of patient.

Figure 2.c: Error message.

Figure 2.d: Create ticket section.

Figure 2.e: Update information section.

Doctor:

If the user login as a doctor he/she will see the main page for doctors (Figure 3.a below). In the main page there is a recipe section where the user can see his/her passed recipes or can create a new one by clicking the ‘Create New Recipe’ button (See on Figure 3.b below). What is more, there is a side bar where the doctor can choose the ‘Tickets’ option to see the tickets came from his/her patients (see on Figure 3.c below) or he/she can choose ‘Create New Ticket’ option to send message to his/her patients (see on Figure 3.d).

Figure 3.a: Doctor main page.

Figure 3.b: Create recipe section.

Figure 3.c: Ticket track.

Figure 3.d: Create Ticket Section.

Pharmacy Company:

If the user enters the system as pharmacy company the main page for the pharmacy company will be displayed by the system with a side bar which contains ‘Add Product’ option where the pharmacy companies can enter their products to the system (see in Figure 4.a below), ‘Products’ option where the pharmacy companies can view their products which are currently in the system (see in Figure 4.b below), ‘Create New Ticket’ option where pharmacy companies can send messages to their customer/patients and doctors (see in Figure 4.c below) and finally ‘Ticket’ option where pharmacy companies can view the messages that they send (see in Figure 4.d below).

Figure 4.a: Add Product Section.

Figure 4.b: View Product Section.

Figure 4.c: Create Ticket Section.

Figure 4.d: View Ticket Section.

Admin:

If the user enters the system as an admin the system will display the main admin page (Figure 5.a below) where it shows the total amount of users, total amount of products and total amount of tickets in the system. It also has a side bar where it contains ‘Settings’ option where admin can change the settings of the system, ‘Backup’ option where the user can take backup of the system, ‘Records’ option where admin can view the log options of the users (see in Figure 5.b below), ‘Users’ option where the admin view user information and can create a new user (see in Figure 5.c), ‘Products’ option where the admin can view and edit products in the system (see in Figure 5.d below) and finally ‘Tickets’ option where admin can view the tickets in the system (see in Figure 5.e below).

Figure 5.a: Admin main page.

Figure 5.b: Log records section.

Figure 5.c: User information.

Figure 5.d: Product information.

Figure 5.e: Ticket section.

# 8. DISCUSSION

Other than improving the overall quality of healthcare, this system can be applied to general governmental health-related areas. As a result the financial flow can be observed, people who do not have the economic capacity to buy certain services can be more easily targeted and helped and also the imbalances among people rising because of some people favoring others as an action of human nature will be eliminated. All healthcare functionalities can be controlled from a general single source and budget reserved for healthcare operations can be easily computed. The difficult and unreliable money transactions done by cash will be automated by card and will become more efficient to track.

Today many industries use recognized financial practices such as NPV to guide decisions on whether to pursue commercialization of a new technology. The same strategies can be appllied to this project.When releasing this project to the software market, our initial goal is to make healthcare accessible to everyone around the world. If this project is to be commercialized, this may result in producing more ways of reaching various drug companies and enlarging our service range which in the end this advantage may translate into significant financial or operational benefits. If this project is commercialized and grow into a much larger version of itself, it may effect the income distribution emerge from healthcare market activity. This project may also introduce concepts like pre-paid care. The risks that may arise from the commercialization of this project is that the difference between poor and non-poor is not always clear or stable and this may lead to actually eliminating some people that actually need help. A fake prescription event can be given as another example to the possible risks in the system.

Although similar systems currently exist in the market, we will implement some additional functionalities that may be subjected to patent. Since this is a software project utility model and industrial design registration do not apply to our system. Any collobration with other companies that require these issues will be handled by that company.

This project will bring many convenience to the social life and healthcare sector since everything will be able to be handled at the comfort of individual’s own home. Organizations will be able to track and manage their stocks more accurately since all of the computations will be automated by our system rather than manual implementation eliminating issues like  circulation of pharmacies to find the drug that the patient needs, and  performing the service / trade according to the drug status in the stock of the pharmacies registered in the system. Our project can also be used for educational purposes in schools based on healthcare to monitor real life business operations. The project is a 24/7 access system where every pharmacy can participate and aims at increasing customer satisfaction by providing better quality service.

The system we have developed will operate under the supervision of the Ministry of Health, and every validated pharmacy and pharmacy warehouse will be able to join to our system and carry out their own trade with the drugs they have and will serve their customers. The system makes money transactions and providing healthcare very convenient. Although we will eliminate majority of the safety and security issues like fake prescriptions and other insurance related problems , people who want to misuse this system may come up with other creative solutions that may concern human health. Every customer should be aware of these issues and make purchasing cautiously.

# 9. CONCLUSION

The project is basically for everyone having any interest or interaction with a healthcare related organization. It performs operations like drug purchasing, simple diagnostics through discussion boards and provide a basic medicine market through many other functionalities listed in this report. It is a usefull application since it makes everything more accurate and more convenient. This project can be improved a lot more and the  only limiting factor is our imagination . Sadly we still have to take the ethical and legal issues into account and reduce some of the improvements that we have made. The overall project is still able to compete in the software market.

To give a more personalized information, we learned how a real life project is organized and managed. We learned deep concepts of documentation and designing diagrams. . While working on this Project, we gained more thorough knowledge on formulating and implementing Test Plans, working with a Database as well as running/using SQL function/queries, better understanding of  Modelio and draw.io and much more intangible but future-oriented benefits. We understand how important it is to catch up with the deadlines and minimize ( and hopefully avoid ) penalties. To conclude, our team feels that this project improved our vision about real life software projects and work environment.

# 10. REFERENCES

List your references. You should cite these mainly in the introduction part.

# APPENDICES

- Instructions for installing the system

E-Commerce for Medicine Shopping System is a web-based system so it requires no installation. In order to access to the system all you need is an access to the internet on any desired device. For XAMPP installation please check the text file inside our project folder.

- Code for the system

<!DOCTYPE html>

<html lang="en">

<head>

<meta charset="UTF-8">

<meta http-equiv="X-UA-Compatible" content="IE=edge">

<meta name="viewport" content="width=device-width, initial-scale=1, shrink-to-fit=no">

<title>{$site_title}</title>

<meta name="keywords" content="{$meta_keywords}" />

<meta name="description" content="{$meta_description}">

<!-- Favicon -->

<link rel="icon" type="image/x-icon" href="templates/{$template}/assets/images/icons/favicon.ico">

<!-- Plugins CSS File -->

<link rel="stylesheet" href="templates/{$template}/assets/css/bootstrap.min.css">

<link rel="stylesheet" type="text/css" href="assets/css/dataTables.bootstrap4.min.css">

<!-- Main CSS File -->

<link rel="stylesheet" href="templates/{$template}/assets/css/style.min.css">

<link rel="stylesheet" type="text/css" href="templates/{$template}/assets/vendor/fontawesome-free/css/all.min.css">

<script type="text/javascript" src="templates/{$template}/assets/js/jquery.min.js"></script>

<script type="text/javascript" src="assets/js/jquery.dataTables.min.js"></script>

<script type="text/javascript" src="assets/js/dataTables.bootstrap4.min.js"></script>

<style>

.cart-dropdown .dropdown-toggle::after{

display: none;

content:'';

}

.header-contact::after{

width:0px

}

</style>

</head>

<body>

<div class="page-wrapper">

<header class="header">

<div class="header-top">

<div class="container">

<div class="header-left header-dropdowns">

<div class="header-dropdown">

<a href="#">{$cookie['currency']}</a>

<div class="header-menu">

<ul>

{foreach $currencies as $currency}

<li><a href="?setcurr={$currency->code}">{$currency->code}</a></li>

{/foreach}

</ul>

</div><!-- End .header-menu -->

</div><!-- End .header-dropown -->

{if $enable_lang}

<div class="header-dropdown">

<a href="#"><img src="templates/{$template}/assets/images/flags/{if $cookie['language'] == "english"}en{else}tr{/if}.png" alt="England flag">{$LANG['language']}</a>

<div class="header-menu">

<ul>

<li><a href="?setlang=english"><img src="templates/{$template}/assets/images/flags/en.png" alt="England flag">{$LANG['english']}</a></li>

<li><a href="?setlang=turkish"><img src="templates/{$template}/assets/images/flags/tr.png" alt="France flag">{$LANG['turkish']}</a></li>

</ul>

</div><!-- End .header-menu -->

</div><!-- End .header-dropown -->

{/if}

</div><!-- End .header-left -->

<div class="header-right">

<div class="header-dropdown dropdown-expanded">

<a href="#">{$LANG['links']}</a>

<div class="header-menu">

<ul>

<li><a href="contact.php">{$LANG['contact']}</a></li>

{if $loggedin}

<li><a href="clientarea.php">{$LANG['clientarea']}</a></li>

<li><a href="logout.php">{$LANG['logout']}</a></li>

{else}

<li><a href="login.php">{$LANG['login']}</a></li>

<li><a href="register.php">{$LANG['register']}</a></li>

{/if}

</ul>

</div><!-- End .header-menu -->

</div><!-- End .header-dropown -->

</div><!-- End .header-right -->

</div><!-- End .container -->

</div><!-- End .header-top -->

<div class="header-middle">

<div class="container">

<div class="header-left">

<a href="index.php" class="logo">

<img src="assets/img/{$logo}" alt="Porto Logo" style="max-height:60px">

</a>

</div><!-- End .header-left -->

<div class="header-center">

<div class="header-search">

<a href="#" class="search-toggle" role="button"><i class="icon-magnifier"></i></a>

<form action="products.php" method="get">

<div class="header-search-wrapper">

<input type="search" class="form-control" name="pname" id="q" placeholder="{$LANG['search']}..." required>

<div class="select-custom">

<select id="cat" name="cid" class="text-capitalize">

<option value="0">{$LANG['allcategories']}</option>

{foreach $categories as $c}

<option value="{$c->category_id}">{ucfirst($c->category_name)}</option>

{/foreach}

</select>

</div><!-- End .select-custom -->

<button class="btn" type="submit"><i class="icon-magnifier"></i></button>

</div><!-- End .header-search-wrapper -->

</form>

</div><!-- End .header-search -->

</div><!-- End .headeer-center -->

<div class="header-right">

<div class="header-contact">

<span>{$LANG['callusnow']}</span>

<a href="tel:#"><strong>{$company_phone}</strong></a>

</div><!-- End .header-contact -->

</div><!-- End .header-right -->

</div><!-- End .container -->

</div><!-- End .header-middle -->

</header><!-- End .header -->

<main class="main">

<div class="info-boxes-container">

<div class="container">

<div class="info-box">

<i class="icon-shipping"></i>

<div class="info-box-content">

<h4>{$LANG['freeship']}</h4>

<p>{$LANG['freeshipd']}</p>

</div><!-- End .info-box-content -->

</div><!-- End .info-box -->

<div class="info-box">

<i class="icon-us-dollar"></i>

<div class="info-box-content">

<h4>{$LANG['moneyback']}</h4>

<p>{$LANG['moneybackd']}</p>

</div><!-- End .info-box-content -->

</div><!-- End .info-box -->

<div class="info-box">

<i class="icon-support"></i>

<div class="info-box-content">

<h4>{$LANG['onlinesup']}</h4>

<p>{$LANG['onlinesupd']}</p>

</div><!-- End .info-box-content -->

</div><!-- End .info-box -->

</div><!-- End .container -->

</div><!-- End .info-boxes-container -->

<div class="container">

<div class="row">

<div class="col-md-12">

<h3 class="text-center text-uppercase">ALL PRODUCTS</h3>

</div>

<div class="col-md-12">

<div class="product-wrapper">

<div class="product-intro divide-line up-effect">

{foreach $products as $p}

<div class="col-6 col-md-3 product-default">

<figure>

<a href="product.php?pid={$p->product_id}">

{if $p->product_img ==''}

<img src="storage/img/noimg.jpg">

{else}

<img src="storage/img/{$p->product_img}">

{/if}

</a>

<!-- <span class="product-label label-sale">27% OFF</span> -->

</figure>

<div class="product-details">

<div class="category-list">

<a href="products.php?cid={$p->category_id}" class="product-category">{$p->category_name} (Category)</a>

</div>

<div class="category-list">

<a href="javascript:void(0)" class="product-category show-company"

data-cname="{$p->company_name}"

data-cemail="{$p->company_email}"

data-ccountry="{$p->company_country}"

data-ccity="{$p->company_city}"

data-caddress="{$p->company_address}"

data-cphone="{$p->company_phone}"

>{$p->company_name} (Company)</a>

</div>

<h2 class="product-title">

<a href="product.php?pid={$p->product_id}">{$p->product_name}</a>

</h2>

<div class="price-box">

<span class="product-price">{$p->price} {$p->curr_code}</span>

</div><!-- End .price-box -->

<div class="product-action">

<a href="order.php?pid={$p->product_id}" class="btn-icon btn-add-cart text-uppercase"><i class="icon-bag"></i>{$LANG['addcart']}</a>

</div>

</div><!-- End .product-details -->

</div>

{/foreach}

</div>

</div>

</div>

</div><!-- End .row -->

</div><!-- End .container -->

<div class="mb-4"></div><!-- margin -->

</main><!-- End .main -->

<div id="show-company" class="modal" tabindex="-1" role="dialog">

<div class="modal-dialog" role="document">

<div class="modal-content">

<div class="modal-header">

<h2 class="modal-title">Company Information</h2>

<button type="button" class="close" data-dismiss="modal" aria-label="Close">

<span aria-hidden="true">&times;</span>

</button>

</div>

<div class="modal-body">

<div class="row">

<div class="col-md-12">

<ul>

<li>Company Name : <span id="cname"></span></li>

<li>E-mail : <span id="cemail"></span></li>

<li>Country : <span id="ccountry"></span></li>

<li>City : <span id="ccity"></span></li>

<li>Address : <span id="caddress"></span></li>

<li>Phone : <span id="cphone"></span></li>

</ul>

</div>

</div>

</div>

</div>

</div>

</div>

<script>

$(".show-company").click(function () {

$("#cname").html($(this).data('cname'));

$("#cemail").html($(this).data('cemail'));

$("#ccountry").html($(this).data('ccountry'));

$("#ccity").html($(this).data('ccity'));

$("#caddress").html($(this).data('caddress'));

$("#cphone").html($(this).data('cphone'));

$("#show-company").modal();

});

</script>

<footer class="footer">

<div class="footer-middle">

<div class="container">

<div class="footer-ribbon">

{$LANG['getintouch']}

</div><!-- End .footer-ribbon -->

<div class="row">

<div class="col-lg-12">

<h4 class="widget-title">{$LANG['contactus']}</h4>

</div>

<div class="col-lg-3">

<div class="widget">

<ul class="contact-info">

<li>

<span class="contact-info-label">{$LANG['address']}:</span>{$company_address}

</li>

</ul>

</div><!-- End .widget -->

</div><!-- End .col-lg-3 -->

<div class="col-lg-3">

<ul class="contact-info">

<li>

<span class="contact-info-label">{$LANG['phone']}:</span>{$LANG['free']}<a href="tel:">{$company_phone}</a>

</li>

</ul>

</div>

<div class="col-lg-3">

<ul class="contact-info">

<li>

<span class="contact-info-label">Email:</span> <a href="mailto:mail@example.com">{$company_mail}</a>

</li>

</ul>

</div>

<div class="col-lg-3">

<ul class="contact-info">

<li>

<span class="contact-info-label">{$LANG['workingdays']}:</span>

{$LANG['monday']} - {$LANG['friday']} / 09:00 - 20:00

</li>

</ul>

</div>

</div><!-- End .row -->

</div><!-- End .container -->

</div><!-- End .footer-middle -->

<div class="container">

<div class="footer-bottom">

<p class="footer-copyright">{$site_title} &copy;  {date('Y')}.  {$LANG['allrights']}</p>

<img src="templates/{$template}/assets/images/payments.png" alt="payment methods" class="footer-payments">

</div><!-- End .footer-bottom -->

</div><!-- End .container -->

</footer><!-- End .footer -->

</div><!-- End .page-wrapper -->

<div class="mobile-menu-overlay"></div><!-- End .mobil-menu-overlay -->

<a id="scroll-top" href="#top" title="Top" role="button"><i class="icon-angle-up"></i></a>

<!-- Plugins JS File -->

<script src="templates/{$template}/assets/js/bootstrap.bundle.min.js"></script>

<script src="templates/{$template}/assets/js/plugins.min.js"></script>

<!-- Main JS File -->

<script src="templates/{$template}/assets/js/main.min.js"></script>

</body>

</html>