## Slide 1: CMPE 412 Software Engineering
Asst.Prof.Dr.Duygu Çelik Ertuğrul
Room: CMPE 206
Email: duygu.celik@emu.edu.tr

## Slide 2: Project Management
*Bad Management Project
Late Delivery
High Cost FAILURE!!!
Failure to meet requirements
*Plan and Schedule Project Development
  Monitor Progress: Are we going ‘on time’ ? or Are we ‘within the budget’ ?
  Is the work carried out to the required standards?

## Slide 3: Difficulties in software project management
The product is intangible.
  It can’t be seen or touched like a building or a ship.
  The software project managers rely on the progress review reports to measure progress.
There are some standards on software processes for organizations...
  Software processes vary dramatically from one SE company to another.
Large software projects are usually different is some ways from previous projects.
  So, even those managers with a lot of experience may have difficulties.
  Also, rapid changes in computer hardware and communication systems can make the experience ‘obsolete’ (outdated).
  Lessons learned from previous projects may not be transferrable to new projects.
  This situation may create some difficulties in early estimation or upcoming possible risks!

## Slide 4
3 Important Software Project Management Activities
  Project planning and scheduling
  Project monitoring
  Risk management
Software Project Management activities are:
  Proposal writing
  Project planning
  Project scheduling
  4. Risk management
  5. Estimating project cost
  6. Monitoring progress and reviews
  7. Choosing and evaluating team members
  8. Writing reports and making presentations

## Slide 5
Proposal Writing:
  Usually, proposals are written to win a contract.
  The proposal describes the objectives of the project and how it will be carried out.
  It includes cost and timing estimates.
  Risk management and contingency plans.
  There are no guidelines for proposal writing, it is a skill that can be acquired through practice and experience (a part of your term assignment).
Project Planning:
  Concerned with
    identifying the activities
    identifying the milestones
    identifying the deliverables to be produced by the project
  The project plan guides the development towards project goals.
  Resources required are estimated, and accordingly a cost estimate can be made.

## Slide 6
3. Project Monitoring:
Keep track of progress, comparing actual progress with the planned progress.
Keep track of cost, and compare with planned cost.
There are formal mechanism we can use-like weekly or monthly review meetings/reports.
Informal discussion with team members is also essential.

## Slide 7
4. Choosing and evaluating team members:
Ideally: select skilled staff with good experience.
In real-life: accept and be relax for a less-than ideal team.
Possible Reasons of being less-than ideal team:
  The Project budget may not cover high wages use staff with less skills, less experience.
  There may be no experienced staff available.
  It may be impossible to recruit (beginner level) new staff  use the best from within the company.
  The organization may want inexperienced staff members to learn and gain experience, so they are assigned to the Project by the higher administration.
At least one member of the team should have enough experience with the type of system being developed.

## Slide 8
5. Project Planning (more detailed discussion)
Effective management of a SE project depends on systematically planning the progress of the project.
The project plan must be prepared at the beginning when we have incomplete info on the project
later, as more info becomes available, this plan evolves (changes and improves)

## Slide 9: Project Plan For The Development Process: (Suggested Format)
  Introduction: briefly describe the objectives of the project and indicate the constraints (such as time, budget, ….)
  Project organization: describe the way in which the project team is organized: the team members and their roles.
  Risk analysis: describe the possible project risks, the probability of those risks, and the risk reduction strategies.
  Resource requirements (Hardware + Software): specify the hardware and software required to carry out the development. (new hardware may have to be bought --> need to include price and delivery time estimates in the project plan)

## Slide 10
  Work Breakdown: break the project down into activities, identify milestones and deliverables associated with each activity.
  Project Schedule (timing diagram--Gantt chart):
    Show the dependencies between:
      activities,
      estimated time for deliverable and milestones, and
      allocation of people in project.
  Monitoring and reporting mechanisms

## Slide 11
Development plan: (already discussed)
Quality Plan: describes the ‘standards’ and ‘quality procedures’ that will be used in Project life cycle.
Validation (testing) Plan: describes the approach, resources and Schedule for testing / validation of the system.
Configuration management plan
Maintenance Plan: maintenance requirements, costs and effort required.
Staff Development Plan: describes how the skills and experience of the team members will be developed.
Types Of Project Plans

## Slide 12
*Software is intangible -> that is why, the project managers require progress reports and meetings.
*Establish a set of milestones
*When a milestone is reached, some formal output will be produced (e.g. a report)
*A deliverable is a project output(result) that is delivered to the customer.
Milestone???
A recognizable end-point of a software process activity
It can be a short report,
explaining what has completed…
Milestones and Deliverables

## Slide 13
*To establish milestones, the software design process must be broken down into basic activities with associated outputs.
*Example: Milestones in the requirements process, assuming prototyping is used:
Feasibility study
Requirements analysis
Requirement specification
Design study
Prototype development
Feasibility report
Requirements definition
Evaluation report
System architecture design
System requirements

## Slide 14
One of the most difficult jobs for a project manager:
  Estimate the time, human resources and cost to complete each activity,
  Organize these activities into a coherent (intelligible) time sequence.
If the project is very similar to a previous project  good !
  We can generate a close estimate for the Schedule.
However, in general, software projects are quite different, because of:
  Different organizational structures
  Different design methods
  Different team members
  Different implementation tools (e.g., Prog. Lang.)
  Advanced and novel technology involved
Therefore: continually update the Schedule during the progression of the Project.
Project Scheduling

## Slide 15
So, we have to divide the problem into sub problems.
Each Problem is a TASK!
Usually, some tasks may be carried out in parallel, but some are dependent on other tasks (can be seen Gantt chart of the project).
Requirements
Identify activities
Find activity dependencies
Estimate resources for activities
Allocate team members to activities
Create activity charts
Check progress
Charts
Project Scheduling Process

## Slide 16
We define ‘a week’ as the unit of time for activities.
An activity should not take more than 8-18 weeks, otherwise it means we need to divide it additional to subtasks.
When estimating resources;
  human effort,
  hardware resources (e.g.. Disk space) and
  cost should be considered.
There may be problems encountered during the project:
  people working in the team may feel ill, may be demotivated, may leave the company.
  computers may break down, files may be erased, back-up’s may become corrupted.
  hardware / software products purchased may arrive late.
  if you are using new technology, certain parts may take more time than you predicted.
Add an extra contingency factor to cover the losses bcz of these problems...
Sommerville adds 30% to the original estimate for anticipated (expected) problems, and then another 20% to cover unexpected problems.

## Slide 17
Ex: Task durations and dependencies table (T: Tasks, M:Milestones)
Task | Duration(Days) | Dependencies
T1 T2 | 8 15 | - -
T3 T4 | 15 10 | T1(M1) -
T5 T6 | 10 5 | T2,T4(M2) T1,T2(M3)
T7 T8 | 20 25 | T1(M1) T4(M5)
T9 T10 | 15 15 | T3,T6(M4) T5,T7(M7)
T11 T12 | 7 10 | T9(M6) T11(M8)
Activity tables, charts, networks
USE TOOL- MS PROJECT:
Network Chart: https://www.youtube.com/watch?v=ChaLFffUukc
Resource Pool: https://www.youtube.com/watch?v=zcMs4m644tc
Assign Resources: https://www.youtube.com/watch?v=V6wiJP2NsB4
Design Start Date: https://www.youtube.com/watch?v=2MoK081Y050
Add Milestones: https://www.youtube.com/watch?v=ZPVemTpdCGA

## Slide 18
  Consider the problem
  Divide it into sub problems -> activities / tasks
  Estimate the duration for each task
  Find out task dependencies (For example , T3 cannot start before T1 is finished, T1->T3)
Using this table, we can generate an activity (sequence) chart (See. Fig 5.6 on p.102)
Then, generate the activity bar chart (Fig. 5.7, p.103) and staff allocation and time chart (Fig. 5.8, p.104)
For creating this table:

## Slide 19: Activity network

## Slide 20: Activity timeline

## Slide 21: Staff allocation

## Slide 22
MS Project Tool tutorial by Erik Larson:
01 What you see when you open MS Project 2013, here!
02 How to create a WBS, here!
03 How to code a WBS, here!
04 Manual Scheduling vs Auto Scheduling, here!
05 How to Enter Estimated Duration, here!
07 How to enter predecessor information to create a project Schedule, here!
08 How to change a timescale, here!
09 Formatting a Gantt chart, here!
10a Network Sensitivity, here!
10b The difference between free slack and total slack, here!
11 How to introduce lags into a Schedule, here!
12 How to display your Schedule as a Network Diagram, here!
13 How to create a Resource Pool, here!
14 How to assign resources to specific tasks, here!
15 How to designate a start date for a Project, here!
16 How to insert Milestones into your Schedule, here!
17 How to alter the Work Calendar: Entering Holidays, here!
18 Printing and Saving as a PDF Part 1, here!
19 Printing and Saving as a PDF Part 2, here!
20 How to insert Titles and manage Legends when Printing or Saving a PDF, here!
22a How to resolve resource over allocation by Leveling: Overview, here!
22b How to resolve resource over allocation by Leveling: Leveling within slack, here!
22c How to resolve resource over allocation by Leveling: Leveling outside of slack, here!
23 How to access Total Cost information, here!
24 How to generate a Cash Flow chart, here!
25 How to save a Plan as a Baseline, here!
26 How to insert a Status Date, here!
27 How to record actual progress on a Project, here!
28 How to obtain Earned Value performance information, here!
29 How to examine schedule variance in real time, here!
30 How to obtain CPI and SPI, here!
31 Some Major Changes between MS Project 2013 and earlier versions, here!

## Slide 23: Generic Process Framework For SE
Five Activities:
  communication,
  planning,
  modeling/design,
  construction/development,
  deployment
Umbrella Activities: project tracking and control, risk management, quality assurance, configuration management, technical reviews, documentation …
Process Flow: describes how framework activities are organized with respect to sequencing and timing (actions and tasks occur within each activity).
Planning
----------------
Estimation Scheduling
Control / Tracking Issues

## Slide 24
Software Process (e.g. design…)
Process Framework
Umbrella Activities
Framework activity #1
Software eng. Action #1.1
Task Sets 1.1
Software Eng. Action # 1.k
Task Sets 1.k
Framework Activity # n
Work tasks
Work products
Quality assume points
Project milestones

## Slide 25
Process Flow
a)
(Linear) waterfall
b)
Prototype Released (Evolutionary)
planning
planning
modelling
construction
deployment
communicate
communicate
modelling
construction
deployment

## Slide 26
Here,
Communication will stand for:
-obtaining the project description (vendor)
-preparing the bid
-reviewing stakeholders after winning the bidding
-discussing initial requirements
Planning will stand for:
-doing initial analysis - feasibility
-estimates size, cost, human effort, time
-deciding on task scheduling and distribution to team members
Modelling will stand for:
-doing detailed analysis
-developing requirements
-selecting the system architecture (e.g. client / server) and the software type (e.g.PL,DBMS,…..)
-software design
Construction:
-coding
-testing

## Slide 27: Process Models
work flows in a linear fashion
used when the requirements are well understood (e.g. well-defined adaptations or enhancements to an existing system)
Waterfall Linear Model
https://www.youtube.com/watch?v=An7HC1LolDM
http://moodle.autolab.uni-pannon.hu/Mecha_tananyag/szoftverfejlesztesi_folyamatok_angol/ch03.html

## Slide 28: The waterfall model
http://moodle.autolab.uni-pannon.hu/Mecha_tananyag/szoftverfejlesztesi_folyamatok_angol/ch03.html

## Slide 29
Real projects do not usually follow a sequential flow, TROUBLE!
  Changes in requirements in one of the steps means that we have to do many things again…
  Also, it may cause confusion among team members.
At the beginning of many projects, there will be uncertainties and hereafter incomplete requirements may be developed.
A working version of the programs will not be available before delivery, so customer must have patience and can only give feedback when the code is delivered.
Teams have dependent tasks and they must wait for others to finish their parts.
Problems with linear (waterfall) model :

## Slide 30
Classic Waterfall Model With Actions
Communicate
------------------
Project initial
Requirements gathering
Planning
----------------
Estimation Scheduling
Control / Tracking Issues
Modelling
----------------
Analysis req. design
Software Design
Construction
----------------
Coding
Testing
Deployment
---------------
Delivery and training
Maintenance

## Slide 31
Strict market deadlines (e.g. Mobile application development )
  Introduce a limited version, (which will include only the ‘essential requirements’) get a hold on the market,
  Then introduce more developed version covering ‘should do’ requirements as well.
  Note: business or product requirements may change while work is in progress.
Why Prototyping is used:
  A customer defines a set of general objectives for the software, but does not identify/describe detailed requirements for functions / features.
  The developer company may not be sure about the efficiency of an algorithm, or the form human computer interaction should take.
Prototyping (Evolutionary Model)
(*Spiral Model Of development: Boehm)

## Slide 32
Plan 2
Deployment
P2
Construct
Prototype -2
model 2
Feedback
2
Communication
Quick
Plan
Modelling
Quick Design
Construct
Prototype -1
Deployment
P1
Feedback
1
3rd one if neccessary
(*Spiral Model Of development: Boehm)

## Slide 33: Boehm’s spiral model
Process is represented as a spiral rather than as a sequence of activities with backtracking.
Each loop in the spiral represents a phase in the process.
No fixed phases such as specification or design
loops in the spiral are chosen depending on what is required.
Risks are clearly measured and resolved throughout the process.
https://www.youtube.com/watch?v=mp22SDTnsQQ
https://www.youtube.com/watch?v=F5fuUs7oJu0
https://www.youtube.com/watch?v=re4c0BrSfM0#t=426.325435

## Slide 34: Boehm’s spiral model of the software process
https://www.youtube.com/watch?v=mp22SDTnsQQ
Any development model
is chosen here

## Slide 35: Spiral model sectors
Objective setting
  Specific objectives for the phase are identified.
Risk assessment and reduction
  Risks are evaluated and
  Performed some activities to reduce the key risks.
Development and validation
  A development model is chosen which can be any of the generic models.
Planning
  The project is reviewed and the next phase of the spiral is planned.

## Slide 36: Spiral model usage
Spiral model has been very powerful in helping people think about iteration in software processes and
The model introducing the risk-driven approach to development.
The model published as practical software development

## Slide 37: UML(Unified Modeling Language)
James Rumbaugh, Grady Booch, Ivar Jakobson: (1990’s)
An unified modeling method with tools that would cover/combine the best features of their OO analysis and design methods.
The Result: UML an unified modeling language.
It became an industry standard for OO analysis and design (1997’s)

## Slide 38: Agile Development
(Kent Beck, 2001 et al.)  ‘Manifesto for Agile Software Development’
They decide to value/contribute:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan

## Slide 39
Customer satisfaction and early incremental delivery of software,
Small, highly motivated project teams,
Informal methods in customer relations,
Minimal SE work products,
Overall development simplicity
Provide active and continuos communication between the customer and the developers (design team includes customer representatives)
Agile Development encourages:

## Slide 40: Outsourcing
Definition: give some parts of development work to other companies or individuals.
Example: more economical (e.g. testing)

## Slide 41
Advantages Of Protoyping:
  Users / customers get a feeling for the actual system early in the process.
  Developers get to build something immediately.
  Disadvantages Of Prototyping:
    First prototype usually has low quality code and maintainability is weak (creates  Quality problems)
    Software team often makes implementation compromises in order to get the prototype working quickly (creates  Quality problems)
    The PL or OS or algorithm chosen for the first prototype may not be an appropriate one,
    But this non-ideal choice may become an integral (additional/incemental) part of the system and it may be employed in the next prototype as well.
    Project planning is difficult as we may not certainly know how many prototypes will be constructed.

## Slide 42
Note: Parts of some SE process activities like Testing, will start earlier, even when Communication-Requirements Gathering activites is in progress, and goes in parallel with other activities (Planning, Modelling, then, Coding) and then it is completed after Coding is finished.
Note: We may make use of commercial off-the staff (COTS) software components developed by other vendors (Component-based development)
Note: We can use as source modules development in previous projects.

## Slide 43
1. Divide and conquer.
Divide big problems into smaller parts such that each part delivers some distinct functionally, that can be developed and tested independently.
2. Understand and use abstraction.
In analysis and design, we begin with models that represent high levels of abstraction (no details discussed) and we improve those models into lower levels of abstraction.
3. Go for consistency: (e.g. Web application development: menu options should be consistent on all pages, color scheme must be consistent, icons used must be consistent).
4. Focus on the information transfer:
    from OS to the application
    from end user to GUI
    from DB to end user, …
    from one module to another, …
    NOTE: Danger: omission, ambiguity, error, …
    NOTE: Pay special attention to the analysis, design, construction and testing of interfaces.
SE Principles that Guide Practice [Ch#7, Pressman ed.9]

## Slide 44
5. Build software modularly
This is needed to realize the first principle (divide)
Modularity should be effective: each module should focus on one well-constrained feature of the system.
Modules should be interconnected in a relatively simple manner,
Each module should exhibit low coupling to other modules, data sources, peripherals.
6. Code for patterns
Reuse modules / patterns from earlier projects if possible
Also, if we see that a part of our system is similar to a part of another system developed before, we can learn problems encountered and how those problems were solved, without having to go through similar problems again.

## Slide 45
Characterize the problem and its solution from different perspectives:
  This way, greater insight will be achieved into the problem
  errors / omissions can be avoided (e.g.requirements design: scenarios, state diagrams, …. )
Remember: someone will maintain the software.
  For correcting defects, or making enhancements due to customer requests (Maintainability, react quickly and correctly)

## Slide 46
Need to understand well the scope of the project.
Involve stakeholders in the planning activity (bcz. they define constraints and priorities)
Recognize that planning is iterative
  The project plan must be able to accommodate changes
  In prototyping, we have to replan according to feedback that comes from the customer / end users
Estimates are based on what you know
Consider risks as you define the plan.
  If there are risks with high probability causing high impact, contingency planning is needed and,
  you should know how to act in such cases
SE Planning Principles

## Slide 47
Be realistic
  Changes will occur
  People will get in, or they will need breaks from work
Arrange granularity as you define the plan
  Granularity->level of detail
  high-granularity plan is required for short projects that need frequent control (sık kontrol gerektiren kısa projeler için detaylı plan)
  For long projects: low-granularity plan
  Also, we need to know all activities that are around to start…
  For Details-->high granularity plan is needed.
Define how you ensure the quality is under control:
  Schedule technical review meetings
  Sometimes, 2 programmers are given the same task (pair-programming)

## Slide 48
Describe how you plan/intend to arrange changes?
  can the customer request change at any time?
  if a change is requested, shall be implemented it immediately?
  how to assess the impact and the cost of a change?
Track the plan frequently
  i.e. projects fall behind Schedule ‘one day at a time’ !
  so, track progress on a daily basis, if not, at least on a weekly basis.