| Task Name | duration | resources | percentages | Predecessors |
| --- | --- | --- | --- | --- |
| Preliminary investigation |  |  |  |  |
| Lit problems and opportunities | 2days | Project manager | 1 |  |
| Negotiate scope | 1day |  |  | 2 |
| Plan the project | 3days | Project manager | 1 | 3 |
| Present the project and plan | 4days | Project manager, management representative | .50 , .50 | 4 |
| Problem analysis |  |  |  | 1 |
| Understand the current system | 5days | Project manager, system analyzer, user representative | .50 , 1, .50 |  |
| Establish system objectives | 3days | Project manager | 1 | 7 |
| Update project plan | 6days | Project manager | 1 | 9 |
| Present charter completed | 0day |  |  |  |

Resource list

| Resource name | group | COST(STD rate) | Max. unit |
| --- | --- | --- | --- |
| management representative | System owner | 100 TL | 120 |
| user representative | System user | 0 TL | 300 |
| project manager | System analyst | 150 TL | 100 |
| system analyzer | System analyst | 200 TL | 200 |

1. Create a project plan and set the start date of your project to 17, OCTOBER 2019

2. Summarize the task

Preliminary investigation (2-5)

Problem analysis (7-10)

2. Precedence is the classical finish-to-start

3. 10th of November 2019 are non-working days.

4. Link the task to see the milestone.

5. Copy the gantt chart to word processor..

6. Insert deadline date to the last task(07/12/2019)