EASTERN MEDITERRANEAN UNIVERSITY

INFORMATION TECHNOLOGY

MICROSOFT PROJECT

GSM Software Development Company received a contract to design and install a

customer accounting information system from a large Utility Company. The Project

Manager has identified two types of resources, Analyst and Programmer, to be used in the project.

Following table lists the project tasks, their precedence relationships, durations and required resources.

| Task Label | Task Name | Duration (WEEKS) | Predecessor | Analyst (%) | Programmer (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning | 1 | - | 50 | 50 |
| 2 | Meeting | 2 | 1 | - | 100 |
| 3 | Analysis | 1 | 1 | - | 100 |
| 4 | Collecting Document | 2 | 3 | 100 | - |
| 5 | Design | 3 | 3 | 200 | 100 |
| 6 | User Interface | 4 | 4SS-2 | 100 | 150 |
| 7 | Database | 2 | 5;4 | 150 | 100 |
| 8 | Implementation | 1 | 4 | 100 | - |
| 9 | Writing Code | 2 | 6;5 | 100 | 100 |
| 10 | Testing | 2 | 7;8 | 50 | 50 |
| 11 | Support | 1 | 6 | 100 | - |
| 12 | Presentation | 0 | 11 | - | - |

Project start date is determined as Wednesday, 06 NOVEMBER 2019

Schedule the project from the project start date

Analyst and Programmer  are paid at the rate of 75 $/hr and  30 $/hr , respectively.

Precedence is the classical finish-to-start.

All activities are of fixed duration and to be scheduled as soon as possible.

- Summarizing Task

  - PLANNING(2)

  - ANALYSIS(4)

  - DESIGN(6-7)

  - IMPLEMETATION(9-10)

- 14 NOVEMBER 2019 is non-working day.